## Read me
SOCO Recommendation Intelligence Engine ¦ Sprint 1 activity pack
Issued by | Cristo Labs, Data Science Workstream
Audience | SOCO platform and engineering team
Sprint | Sprint 1, Feature and evaluation foundation
Intro on Recommendation Engine
A recommendation engine decides the order things appear in. It improves over time by learning from what people did with the lists it produced.
To learn, it needs three things recorded together: what was shown, in what position on screen, and what the user did next. Logging only the clicks and the purchases is not enough. What the engine actually learns from is the difference between the items that were shown and the item that was chosen. Without the items that were shown and ignored, there is nothing to compare against.
Data that is not captured cannot be recovered later. If a field is added three months after launch, the learning period for anything that depends on it starts from that date, not from launch day.
Sprint 1 does not build any model. It agrees the list of inputs, confirms which of them the current database can actually supply, and agrees how success will be measured.
What is in this workbook
Tab | What it is | What you do with it
Sprint 1 platform tasks | Every activity asked of the platform team in Sprint 1, with the reason for each one in plain language. | Set the Status column on every row. Add a note where something is partly done or named differently.
Cristo Labs checklist | The matching activities on the Cristo Labs side, with the dates they are delivered. | Read only. It tells you what you are waiting on from us and when.
JIRA import | The same platform tasks in JIRA import format, as one epic with stories and sub-tasks. | Adjust dates and assignee, then import. Estimates are in seconds, as JIRA expects.
Decisions needed | Nine questions that need a decision rather than an investigation. | Record the decision and who made it. Six of them block feature definition directly.
Capture register | The field level list of what the app needs to record from launch day. 12 events, 58 fields and 8 data model changes. | Set the Current status on every field row and every data model row.
Wave map | The nine model families across Wave 1A, Wave 1B, Wave 2 and Wave 3, and how the proposal's counts reconcile with what actually ships. | Read it before the Model options tab. It answers what runs on day one and what does not.
Model options | The change to the solution design. Three models run two candidate methods side by side from launch. The rest run one. | Read the At launch and Platform work columns. Only three rows create any work for the platform team.
Exit criteria | What has to be true for Sprint 1 to be considered complete. | Use it as the definition of done.
Status values
Value | Meaning
Not started | No work done yet.
In progress | Started, not finished.
Done | Complete and verifiable.
Blocked | Cannot proceed. Say what is blocking it in the Notes column.
Deferred | A deliberate decision not to do it in Sprint 1. Recorded as a joint decision, not an omission.
Needs discussion | The ask is unclear or disputed. Flag it rather than guessing.
Response summary, updates automatically
Status | Platform tasks | Decisions
Not started | 2 | 2
In progress | 3 | 0
Done | 14 | 7
Blocked | 0 | 0
Deferred | 0 | 1
Needs discussion | 0 | 1
Capture register, section 1 event decisions, 12 rows
Decision | Events
Accepted | 9
Deferred | 1
Needs discussion | 2
Not yet decided | 0
Capture register response, 68 rows in total
Status | Rows
Already captured | 12
Will add | 33
Partially captured | 18
Deferred | 3
Needs discussion | 5
Not yet answered | 0

## Sprint 1 platform tasks
Sprint 1 ¦ Activities for the platform team
Set the Status column on every row. Target day is the working day within the sprint, day 1 being the first day. Effort is an estimate for guidance only and is not a commitment on your behalf.
Ref | Task | What you actually do | Why it is needed, in plain language | Owner | Status | Notes
PT-01 | Issue a read-only database credential | Create a database user on the soco database with read-only rights on the cluster that is authoritative for the launch build. Confirm whether nex-dev is that cluster or whether another one is. | Every other activity in this sprint depends on being able to read the current schema. This is the single dependency dated day 1. | Aravinth | Done | Read-only MongoDB access has been created and verified for the nex-dev SOCo cluster. Connection details have been shared for use by the relevant sprint activities. MongoDB connection URL: mongodb+srv://readonly_user:RevealerSoco1429@nex-dev.cob9whd.mongodb.net/soco
PT-02 | Send schema definitions for the empty collections | Export and send the Mongoose schema definitions for userevents, taggedposts, influencerearnings, referrallinks, postreports, followers and storefollows. Also say which of these are deprecated and should be ignored. | These collections exist but hold no documents, so we cannot tell what fields they carry by reading them. | Aravinth | Done | Completed the schema definitions for 60 collections and shared the schema details in a PDF for reference.
PT-03 | Close the six blocking decisions | Work through Q01 to Q06 in the Decisions needed tab and record an answer against each. These are product and data model decisions, not investigations. | Each one determines which fields the models are allowed to read. Guessing an answer and correcting it later means redoing the feature work. | Platform and client | In progress | Q01, Q02, Q03, Q04, Q06 and Q10 answered; Q05 remain.
PT-04 | Nominate the canonical order outcome field | The orders collection carries four status fields: order_status, payment_status, seller_delivery_status and buyer_approval_status. Name the one that defines a completed sale, and supply the full list of values it can hold and what each means. | The engine has to know what counts as a successful purchase before it can be told to aim for one. With four parallel fields and no stated precedence, there is no single definition of a completed order, so no target can be defined and no quality threshold can be set. | Aravinth | Done | Canonical field: order_status Four status fields exist on the Order model with no stated precedence: order_status, payment_status, seller_delivery_status, buyer_approval_status. After reviewing all four: order_status is nominated as the authoritative outcome field. Full value list: Pending → Accepted → Confirmed → Shipped → Delivered / Cancelled / Rejected / Processing / Payed Off / Out for Delivery Successful purchase = order_status: "Delivered" Written atomically by DeliveredBySeller endpoint. Already used as the revenue and conversion floor across all dashboard analytics. This is the value the engine must aim for. The other three fields are operational only and must not be used as outcome signals: payment_status — set manually by seller, frequently null on delivered orders seller_delivery_status — redundant, no enforced sync with order_status buyer_approval_status — covers only the quote-confirmation step, not final delivery Returns are out of scope for this sprint. No Returned or Refunded state exists in the current enum — these will be added in a later phase and will not affect the success definition above.
PT-05 | Complete the launch data capture checklist | Go to the Capture register tab in this workbook. It lists 12 events, 58 fields and 8 data model changes. Set the Current status on every field row and every data model row, and return the workbook. Mark anything you will not do as Deferred rather than leaving it blank. | This is the list of what the app needs to record from launch day. Anything marked Deferred is recorded as a joint decision with the consequence stated. | Aravinth | Done
PT-06 | Confirm which features are computable | Cristo Labs will circulate a launch feature list. Against each row, mark one of three verdicts: computable from the current schema, computable after a named change, or not computable. Where it is computable after a change, name the change. | A feature is a single input to a model, for example how many times this user viewed this category in the last 30 days. If we specify features the database cannot supply, that work becomes immaterial. | Aravinth | Not started
PT-07 | Confirm launch surface and latency budget | Confirm which surface goes live first, for example the main feed or the product listing. Publish the time budget available for the recommendation call on that surface, in milliseconds, broken down by stage. | The time budget sets how large a model is allowed to be. Without it we could specify something accurate that is too slow to serve, which is only discovered at integration. | Allen and Aravinth | Done | Answered 4 September. Feed runs 300 to 600ms today. Budget 200ms for the ranking call with a 200ms timeout and fallback to the delivered ordering. Provisional until RE-00e measures it, and to be restated at p95 and split by stage.
PT-08 | Fix two critical data defects | D01: posts.userId is stored as a string while users._id and orders.user_id are ObjectId. D09: the attribution fields on postevents, being product_id, order_id, session_id, referral_code, view_duration_seconds, viewer_city, viewer_gender and viewer_district, are defined in the schema but null on every document. | D01 makes joins between posts and users return nothing rather than raising an error, so the failure is silent. D09 means the attribution design is correct but nothing writes to it. Neither of these fixes itself when real users arrive. Both are code changes. | Aravinth | Done | D01 — posts.userId stored as String, not ObjectId: Confirmed in the schema — createPostModel defines userId: { type: String, required: true } (createPostModel.js:105), while users._id and orders.user_id are ObjectId. Any $lookup or query joining posts to users by this field returns nothing silently — Mongoose does not raise a cast error when comparing String to ObjectId, it just matches zero documents. Fix: Change userId on the post schema to { type: mongoose.Schema.Types.ObjectId, ref: "users" } and run a migration to cast existing string values. All controllers that write userId at post creation must also pass an ObjectId, not a string. D09 — Attribution fields defined in PostEvent schema but null on every non-view document: Confirmed — product_id, order_id, session_id, referral_code, view_duration_seconds, viewer_city, viewer_gender, viewer_district are all defined with default: null (influencerAnalyticsModel.js:18–28). For view events, viewer_city, viewer_gender, viewer_district, and session_id are correctly populated via demographic lookups in trackPostView (postEngagementController.js:217). For all other events (like, save, share, add_to_cart, purchase) fired via fireAnalyticsEvent, product_id and order_id are passed where available, but referral_code, view_duration_seconds, viewer_city, viewer_gender, and viewer_district are never passed — the fireAnalyticsEvent call in trackPostAction only includes {influencer_id, post_id, event_type, user_id, product_id, order_id, referral_code, session_id} — demographic fields are missing. Fix: Extend trackPostAction to perform the same demographic lookup that trackPostView does and pass all attribution fields into fireAnalyticsEvent. | Removed 3 redundant fields from createPostModel: productId (String) — removed, replaced by products[] array isUserPost (Boolean) — removed, covered by userModel isBusinessPost (Boolean) — removed, covered by userModel description, webSiteLink, isBusinessAccount kept — still actively used in API responses. Status: ✅ Done
PT-09 | Nominate a named contact and agree schema change notice | Agreement to be made with Aravind that the data science workstream is notified before any collection level schema change, rather than discovering it when a query breaks. | Pipeline work built against a schema that changes without notice breaks silently. A notice rule costs nothing and removes a recurring class of rework. | Aravinth | Done | Aravinth is the point of contact from Platform team and he will be providing the updates as and when any schema changes arise
PT-10 | Confirm the serving contract can carry two variants, driven by configuration | Confirm three things. 1) two candidate methods can be live at the same time on one surface, with the traffic split between them, and the identifier stamped on each served list says which one produced it. 2) the split and the default are configuration values read at request time rather than constants compiled into the code. 3) a request is assigned to a method by a hash of the user identifier rather than at random, so a user stays with the same method across a session. At launch this applies to three model slots only: interest, product ranking and promoter score. | Configuration rather than code is the whole point. Changing which method serves should be editing a value, not cutting a release. Hash assignment matters because random assignment reshuffles every user whenever the split changes, which destroys the comparison already in progress. The same mechanism also lets the tuning values inside each method be adjusted as data accumulates, which is usually a larger quality gain than swapping the method outright. See the Model options tab. | Allen | Not started
PT-11 | Confirm three findings against the database | Confirm the order status enum with all its values and the precedence between the four status fields, whether the trackings collection is live and populated and what writes to it, and which follow model the application actually writes to. | The ML schema reference and the database profiling disagree on all three. | Aravinth | Done | Finding 1 — Order status enum and four parallel fields: order_status is the authoritative field with 10 values: Pending, Accepted, Processing, Shipped, Payed Off, Out for Delivery, Delivered, Cancelled, Rejected, Confirmed (orderModel.js:126). Three additional parallel fields exist with no defined precedence: seller_review_status (enum: Pending/Shipped/Reviewed/Accepted/Delivered/Rejected), buyer_approval_status (enum: Pending/Accepted/Rejected/Rejected By Seller), and boolean flags is_Shipped, is_Delivered, is_Payment. Controllers write all four independently — none reads from another. order_status is the field used in all dashboard queries and business logic, confirming it as the authoritative one. Finding 2 — Trackings collection: TrackingModel (Tracking collection) is live. Schema stores sentPosts: [{ post_id, viewedAt, isWatched }] (TrackingModel.js:5). One active writer: postEngagementController.trackPostView — fires on every deduplicated view, pushes { post_id, viewedAt, isWatched: true } (postEngagementController.js:177). Deduplication guard: only records if no prior entry with isWatched: true exists for that user+post pair. One dead writer: The old feedController.js code that pushed isWatched: false entries (feed-served records, not watched records) is fully commented out — that path no longer runs. Any existing documents with isWatched: false are legacy and must not be treated as "already seen" by dedup logic (the current guard correctly checks isWatched === true only). Critical gap — position is not recorded: The schema has no position field. When a view is written, there is no record of where the post appeared in the feed list (position 1 vs position 15). Without this, the ML model cannot correct for position bias — a like on post #1 looks identical to a like on post #14, even though the latter is a far stronger genuine interest signal. Fix: Add position: { type: Number, default: null } to the sentPosts sub-schema, accept position in the trackPostView request body, and have Flutter pass the list index at the time of the view event. This also satisfies F11 and F18 from the event spec. Finding 3 — Which follow model the app actually writes to: Two models exist — FollowModel and followerModel. The app writes to both, depending on the path: a normal follow (no permission required) writes to FollowModel only (followService.js:110). A follow request (private account) writes to followerModel with status: "requested" (followService.js:58). On unfollow, FollowModel is the primary delete target and followerModel is cleaned up as a secondary. The feed (getDashboardFeed) reads exclusively from FollowModel (feedController.js:556) — followerModel is never read by the feed.
RE-00a | Set up the engine repository and environment | Create the repository, the local and deployed environments, the deployment target, and confirm the runtime and language the recommendation service will be written in. | It is the one piece of setup blocked by nobody, so it belongs here rather than competing with build work later. | Allen | In progress | Architecture: Build the service separately in Python, not as a monorepo.
RE-00b | Verify access and profile the collections the engine reads | Connect with the credential issued in PT-01, confirm every collection the engine will read is reachable, and record document counts, index coverage and read times on the ones it will query at request time. | It confirms the credential works and establishes what a query actually costs before any method is designed around it. | Allen | Done | Access verified — connected in 777ms; request completed in 52–54ms.
RE-00c | Read the delivered interest scoring and feed ordering code | Read how the existing interest score and the feedScore, engagementScore and conversionScore fields are computed, and how /dashboard-feed builds its ordering today. | That ordering is the fallback the whole system degrades to and must not be broken. Reading it also answers Q01 in practice rather than in principle. | Allen | Done | Two independent scoring systems, and they are not connected
RE-00d | Agree the API contract and the event ingest endpoint with Aravindh | Agree the request and response shape between the app and the recommendation service, and agree the single endpoint all twelve events are written to. | Both sides build against it from Sprint 2 onward. The ingest endpoint is not a row in the capture register, and nothing there can be marked done until it exists. | Allen | In progress | SOCO_Feed_API_Documentation.pdf
RE-00e | Measure current call latency on the launch surface | Measure what /dashboard-feed takes today, end to end, and compare it against the budget published in PT-07 to establish what headroom the recommendation call actually has. | The published budget is a target. What is left after the existing call is what the engine can really use. | Allen | Done | Also confirms the 200ms ranking budget from PT-07 and restates it at p95, split by stage.
RE-00f | Draft the service design | Module layout, configuration, how a method is loaded into a replaceable slot, how a variant is selected per request, and where scores are read and written. | It is the design Sprint 2 builds. Drafting it here means the first Sprint 2 task starts as construction rather than as design. | Allen | Done | SOCO_Reco_Service_Design_RE00f.pdf
PT-12 | Confirm what the payment webhook will write when it is built | Confirm which field on the order the Razorpay webhook will set at settlement, whether it is the existing is_Payment boolean or a status enum, whether a timestamp is written at the moment of settlement, and whether failure and reversal are captured or only success. Also confirm how a value written by the webhook can be told apart from one entered manually by a seller. | The promoter score is the consumer, not the feed. A promoter's referred sales are only worth crediting once the money has arrived, and commission already runs pending, approved, paid. Without a settled state the score rewards volume rather than realised sales. PT-04 records that payment_status is set manually by sellers and is often blank, so if the webhook writes to the same field the two become indistinguishable and neither can be trusted. This is not blocking for launch: if the state is unavailable, the commercial impact component is defined over Delivered orders instead and the limitation is recorded. | Aravinth | Done | Answered in Sept 4 - Q3. payment_status is the enum and is authoritative. No webhook exists; payment is confirmed by an app call. No further platform action requested.
PT-13 | Confirm where a block is enforced for retrieval that does not read the follow graph | Confirm whether anything other than the deletion of follow edges enforces a block, and confirm that isMuted on followerModel is never written, so it can be removed from the design rather than treated as available. | Block is enforced today by deleting the follow edges between two users in both directions. That protects anything reaching a user through the follow graph, which is how the feed works now. The engine also assembles candidates by attribute similarity to items the user already engaged with, and that path never reads the follow graph, so nothing in it knows a block exists. The block record sits on followerModel with status blocked, while the engine reads FollowModel. Left as it is, a blocked person's post can reach a user through a feature we introduced. The exclusion has to be explicit in the eligibility rules, reading the block records directly. | Allen and Aravinth | Done | Answered in Q10 and Q11. The for you feed does not check the block list. The resulting fix is on the questions for Sept 4 tab, question 10 column H. Mute is not usable and is removed from the design.

## Cristo Labs checklist
Sprint 1 ¦ Cristo Labs activities
The matching activities on the Cristo Labs side. This is both an internal checklist and a status update for the platform team, so it is clear what is being produced and what it is waiting on.
Ref | Activity | Deliverable | Waiting on | Status | Notes
CL-01 | Re-profile the launch subset of the database | Refreshed field verdict per required attribute, confirmed against the current build rather than the earlier inspection | PT-01 | Done | Profiling run 3 September, 35 checks. Follow up run and the fourteen platform answers of 4 September complete the verification. Findings fold into CL-02 as the evidence column.
CL-02 | Produce the launch feature list | One row per feature: reference, model family served, source collection or event, transformation, aggregation window, expected range, refresh requirement, behaviour when the source is null | PT-01, PT-02 | In progress
CL-03 | Classify each feature by readiness | Each feature marked as computable at launch, computable after named instrumentation, or not computable, so that PT-06 is a bounded confirmation rather than an open review | CL-02 | Not started
CL-04 | Circulate the launch feature list | Feature list issued to the named engineering contact with the response window stated | CL-03, PT-09 | Not started
CL-05 | Design the evaluation protocol | Metric set per model family, the baseline each is measured against, the splitting protocol, and an explicit statement of what cannot be measured at launch | PT-04 | Not started
CL-06 | Set acceptance thresholds | Two separate sets. Conformance thresholds that can be checked now on test data. Performance thresholds that can only be set once live traffic exists, stated as a method rather than a number | CL-05 | Not started
CL-07 | Write verification queries | One query per acceptance criterion A1 to A8 in the launch instrumentation requirements, so the platform team can self-check rather than wait for review | CL-02 | Not started
CL-08 | Specify the candidate methods for the three families running two at launch | Written specification of both methods for interest, product ranking and promoter score, the features each consumes, and the conditions under which each is expected to perform better | CL-02 | Not started
CL-09 | Record the second candidate for the remaining six families | A stated position per family, held as methodology rather than as launch scope, to be revisited at the wave gate when the data situation is visible rather than assumed | CL-02 | Not started
CL-10 | Define the selection and promotion policy | The rule that decides which method serves: minimum evidence required, the margin one must beat the other by, how often the comparison is rerun, and the rollback condition. Applies to the three families only | CL-05, CL-08 | Not started
CL-11 | Publish the tunable parameter list | Per launch method, the parameters that are expected to be retuned as data accumulates, each with a default value and a permitted range, so they can be held as configuration rather than as code | CL-02 | Not started
CL-12 | Record the confirmed and deferred set | A single register of what was accepted into the launch build, what was deferred, and the stated consequence of each deferral | PT-05, PT-06 | Not started

## JIRA import
Issue ID | Parent | Issue Type | Summary | Description | Priority | Status | Labels | Component/s | Original Estimate | Start Date | End Date | Due Date | Assignee
3001 |  | Epic | E01 - Recommendation engine Sprint 1, data access, schema confirmation and evaluation foundation | Sprint 1 of the recommendation engine workstream. No model is built in this sprint. The sprint agrees the list of data inputs the models will use, confirms which of them the current database can supply, resolves the blocking product and data model decisions, and agrees how model quality will be measured. Outcome: a launch feature list confirmed as computable by engineering, and an agreed metric and threshold set. | Highest | To Do | rec-engine | Recommendation Engine |  | 31/08/2026 | 11/09/2026 | 11/09/2026
3002 | 3001 | Story | Provide scoped data access and named contacts | Give the data science workstream read-only access to the authoritative database and name a contact for data questions. This is the dependency the rest of the sprint sits behind. | Highest | To Do | rec-engine | Recommendation Engine |  | 31/08/2026 | 31/08/2026 | 31/08/2026
3003 | 3002 | Sub-task | Create a read-only database user on the soco database | Create a dedicated database user with read-only rights on the soco database. Do not reuse the existing shared credential, which carries full administrative rights. Deliverable: connection string issued to the data science workstream. | Highest | To Do | rec-engine | Recommendation Engine | 3600 | 31/08/2026 | 31/08/2026 | 31/08/2026
3004 | 3002 | Sub-task | Confirm which cluster is authoritative for the launch build | State whether nex-dev is the cluster that reflects the launch schema, or name the cluster that does. Deliverable: written confirmation of the cluster name and its purpose. | High | To Do | rec-engine | Recommendation Engine | 1800 | 31/08/2026 | 31/08/2026 | 31/08/2026
3005 | 3002 | Sub-task | Nominate a data contact and agree schema change notice | Name one engineering contact for data and schema questions, and agree that the data science workstream is notified before any collection level schema change. Deliverable: named contact and an agreed notice rule. | Medium | To Do | rec-engine | Recommendation Engine | 1800 | 31/08/2026 | 31/08/2026 | 31/08/2026
3006 | 3001 | Story | Supply schema definitions for the empty collections | Seven collections exist in the database but hold no documents, so their field structure cannot be read by inspection. Supply the schema definitions so the data science workstream is not guessing at them. | High | To Do | rec-engine | Recommendation Engine |  | 01/09/2026 | 01/09/2026 | 01/09/2026
3007 | 3006 | Sub-task | Export Mongoose schema definitions for seven empty collections | Export the schema definitions for userevents, taggedposts, influencerearnings, referrallinks, postreports, followers and storefollows. Deliverable: schema definitions sent, one per collection. | High | To Do | rec-engine | Recommendation Engine | 3600 | 01/09/2026 | 01/09/2026 | 01/09/2026
3008 | 3006 | Sub-task | Confirm which empty collections are deprecated | State which of the empty collections are no longer in use and should be ignored, and which are expected to populate at launch. Deliverable: a live or deprecated marking against each. | Medium | To Do | rec-engine | Recommendation Engine | 1800 | 01/09/2026 | 01/09/2026 | 01/09/2026
3009 | 3001 | Story | Close the blocking product and data model decisions | Six questions require a decision rather than an investigation. Each one determines which fields the models are allowed to read, so an answer changed later means redoing the feature work. | Highest | To Do | rec-engine | Recommendation Engine |  | 02/09/2026 | 02/09/2026 | 02/09/2026
3010 | 3009 | Sub-task | Q01 Decide whether the existing feed ordering is in scope | posts.feedScore, engagementScore and conversionScore already exist and are indexed, so a ranking mechanism is already live. Decide whether the recommendation workstream replaces it, tunes it, or leaves it alone. Deliverable: recorded decision. | Highest | To Do | rec-engine | Recommendation Engine | 1800 | 02/09/2026 | 02/09/2026 | 02/09/2026
3011 | 3009 | Sub-task | Q02 Decide whether a campaign is a real entity in the product | No campaign collection exists anywhere in the schema. Brand to promoter matching has no subject without one. Decide whether campaigns are being built, and if not, that matching is restaged. Deliverable: recorded decision. | Highest | To Do | rec-engine | Recommendation Engine | 1800 | 02/09/2026 | 02/09/2026 | 02/09/2026
3012 | 3009 | Sub-task | Q03 Confirm where the post to product link lives | taggedposts is empty, posts.productId is null and posts.products is an empty list. Three candidate locations, none populated. Confirm the intended one. Deliverable: named field and confirmation it will be populated at launch. | Highest | To Do | rec-engine | Recommendation Engine | 1800 | 02/09/2026 | 02/09/2026 | 02/09/2026
3013 | 3009 | Sub-task | Q04 Confirm whether an order can contain more than one product | orders carries a single product_id rather than a line item array. Confirm whether a multi item basket splits into separate order documents. Deliverable: recorded confirmation, since it determines whether items bought together can be identified at all. | Highest | To Do | rec-engine | Recommendation Engine | 1800 | 02/09/2026 | 02/09/2026 | 02/09/2026
3014 | 3009 | Sub-task | Q05 Confirm the commission record | influencerearnings exists and is empty, and there is no commissions collection. Confirm whether influencerearnings is the intended commission record and what states it carries. Deliverable: recorded confirmation. | High | To Do | rec-engine | Recommendation Engine | 1800 | 02/09/2026 | 02/09/2026 | 02/09/2026
3015 | 3009 | Sub-task | Q06 Nominate the canonical order outcome field and its values | Four status fields exist on orders with no stated precedence. Name the one that defines a completed sale and supply the full value enumeration with the meaning of each value. Deliverable: named field and value list. Every commerce target and quality threshold depends on this. | Highest | To Do | rec-engine | Recommendation Engine | 3600 | 02/09/2026 | 02/09/2026 | 02/09/2026
3016 | 3001 | Story | Complete and return the launch data capture checklist | A separate workbook lists 58 fields across 12 events plus 8 data model changes that the app needs to record from launch day. Set a status against every row and return it. | High | To Do | rec-engine | Recommendation Engine |  | 03/09/2026 | 07/09/2026 | 07/09/2026
3017 | 3016 | Sub-task | Set status on the 58 rows of the field register | Go through each field and mark it as already captured, will add, partially captured, deferred or needs discussion. Add a note where the field exists under a different name. Deliverable: completed field register. | High | To Do | rec-engine | Recommendation Engine | 10800 | 03/09/2026 | 04/09/2026 | 04/09/2026
3018 | 3016 | Sub-task | Set status on the data model changes sheet | These are database changes rather than event logging, so they need a product decision and not only an engineering estimate. Deliverable: completed data model changes sheet. | High | To Do | rec-engine | Recommendation Engine | 5400 | 07/09/2026 | 07/09/2026 | 07/09/2026
3019 | 3016 | Sub-task | Return the completed workbook | Return the workbook to the data science workstream. Anything marked deferred is recorded as a joint decision with its consequence stated, not as an omission. Deliverable: workbook returned. | Medium | To Do | rec-engine | Recommendation Engine | 1800 | 07/09/2026 | 07/09/2026 | 07/09/2026
3020 | 3001 | Story | Confirm which model features are computable from the current schema | A feature is one input to a model, for example the count of views by this user in this category over the last 30 days. Confirm which of the proposed features the database can actually supply, so that unusable ones are removed before work is done on them. | Highest | To Do | rec-engine | Recommendation Engine |  | 08/09/2026 | 10/09/2026 | 10/09/2026
3021 | 3020 | Sub-task | Review the circulated launch feature list | Read the feature list and check each row against the schema you own. Deliverable: reviewed list with queries raised. | Highest | To Do | rec-engine | Recommendation Engine | 10800 | 08/09/2026 | 09/09/2026 | 09/09/2026
3022 | 3020 | Sub-task | Return a verdict against every feature | Mark each feature as computable from the current schema, computable after a named change, or not computable. Where a change is needed, name it. Deliverable: verdict returned against every row, no blanks. | Highest | To Do | rec-engine | Recommendation Engine | 7200 | 10/09/2026 | 10/09/2026 | 10/09/2026
3023 | 3001 | Story | Confirm launch surface and publish the latency budget | Confirm which surface goes live first and how much time the recommendation call is allowed. The time budget sets an upper bound on how large a model may be. | High | To Do | rec-engine | Recommendation Engine |  | 07/09/2026 | 07/09/2026 | 07/09/2026
3024 | 3023 | Sub-task | Confirm which surface launches first | State whether the main feed, the product listing or another surface is the first to carry recommendations. Deliverable: recorded confirmation. It determines which feature work is sequenced first. | High | To Do | rec-engine | Recommendation Engine | 1800 | 07/09/2026 | 07/09/2026 | 07/09/2026
3025 | 3023 | Sub-task | Publish the latency budget per stage in milliseconds | State the total time available for the recommendation call on the launch surface and the split across candidate assembly, scoring and post-processing. Deliverable: published budget. | High | To Do | rec-engine | Recommendation Engine | 5400 | 07/09/2026 | 07/09/2026 | 07/09/2026
3026 | 3001 | Story | Correct two critical data defects | Two defects prevent data being joined or captured at all. Neither resolves when real users arrive, because both are code issues rather than empty tables. | Highest | To Do | rec-engine | Recommendation Engine |  | 09/09/2026 | 11/09/2026 | 11/09/2026
3027 | 3026 | Sub-task | D01 Correct the join key type mismatch between posts and users | posts.userId is stored as a string while users._id and orders.user_id are ObjectId, so joins between posts and users return no rows rather than raising an error. Cast at write time to ObjectId, or confirm a deliberate denormalisation and document it. Deliverable: fix applied or documented decision. | Highest | To Do | rec-engine | Recommendation Engine | 14400 | 09/09/2026 | 10/09/2026 | 10/09/2026
3028 | 3026 | Sub-task | D09 Populate the attribution fields on postevents | product_id, order_id, session_id, referral_code, view_duration_seconds, viewer_city, viewer_gender and viewer_district are defined on postevents but null on every document. Populate them at event emission from the viewer record and the serving context. Deliverable: fields written on new events, verified on a sample. | Highest | To Do | rec-engine | Recommendation Engine | 21600 | 09/09/2026 | 11/09/2026 | 11/09/2026
3029 | 3001 | Story | Confirm the serving contract can carry two variants, driven by configuration | Three model families run two candidate methods side by side from launch: interest, product ranking and promoter score. The other six run a single method. This story confirms the serving and logging side can support two concurrent methods on those three slots, and that the controls are configuration rather than compiled constants. | High | To Do | rec-engine | Recommendation Engine |  | 10/09/2026 | 11/09/2026 | 11/09/2026
3030 | 3029 | Sub-task | Confirm two methods can be live on one slot with a traffic split | Confirm that two methods can serve the same slot at the same time, with each request assigned to one of them and the variant identifier stamped on the served list and every event that follows. Applies to three slots at launch. Deliverable: confirmation, or a named change and its estimate. | High | To Do | rec-engine | Recommendation Engine | 7200 | 10/09/2026 | 10/09/2026 | 10/09/2026
3031 | 3029 | Sub-task | Confirm the split and default are configuration, not compiled constants | The traffic split and the default method must be values read at request time or on a short cache expiry, so that changing which method serves is an edit rather than a release. Deliverable: confirmation of where the values live and how they are changed. | High | To Do | rec-engine | Recommendation Engine | 5400 | 10/09/2026 | 10/09/2026 | 10/09/2026
3032 | 3029 | Sub-task | Confirm assignment is a hash of the user identifier rather than random | A user must stay with the same method across a session and across a change to the split. Random per-request assignment reshuffles every user whenever the split changes and destroys the comparison in progress. Deliverable: confirmation of the assignment method. | High | To Do | rec-engine | Recommendation Engine | 5400 | 11/09/2026 | 11/09/2026 | 11/09/2026
3033 | 3029 | Sub-task | Confirm method tuning values can be held as configuration | Values inside each method, such as the decay rate, component weights and thresholds, are expected to be retuned as data accumulates. Confirm these can be changed without a code deployment. Deliverable: confirmation, or a named change. This is usually a larger quality gain than swapping the method itself. | Medium | To Do | rec-engine | Recommendation Engine | 5400 | 11/09/2026 | 11/09/2026 | 11/09/2026

## Decisions needed
Decisions required in Sprint 1
Each of these requires a decision, not an investigation. Q01 to Q06 block feature definition directly. Record the decision and who made it.
Ref | Question | What prompted it | What it blocks | Owner | Priority | Status | Decision recorded
Q01 | Is the feed ordering already computed by the platform in scope for the recommendation workstream? | posts.feedScore, engagementScore and conversionScore exist and are indexed. A ranking mechanism is already live. | Determines whether the feed ranker replaces, tunes or ignores an existing implementation. It is a scope boundary question as much as a technical one. | Client and platform | P1 | Done | The existing implementation is the fallback mechanism
Q02 | Is a campaign a real entity in the product? | No campaign collection exists among the 65 collections. Promo codes are not campaigns. | Brand to promoter matching ranks promoters for a campaign. Without a campaign object it has no subject and should be restaged to a later wave. | Client | P1 | Deferred | Recorder by Kala, based on the discussions in the call. Campaign entity scheduled approximately one month after launch. Launch date itself is still open under Q09, so this is an offset rather than a fixed date. M7 remains out of Wave 1A as already planned. No change to launch scope. M6 runs at launch over products and services only, with campaign candidates excluded until the entity exists. Engine C activation requires three things, not one: the campaign entity, campaign lifecycle states including a defined completed state, and promoter invitation, acceptance and completion records. If only the entity is delivered, M7's rules form unblocks and its learned form stays blocked indefinitely.
Q03 | Where is the post to product link intended to live? | taggedposts is empty, posts.productId is null and posts.products is an empty list. Three candidate locations, none populated. | Whether the feed can rank shoppable content at all, as opposed to ranking content that happens to sit near products. | Platform | P1 | Done | Initially, posts supported attaching a single product, so we used a productId field. Later, the requirement was changed to support multiple products per post. We therefore introduced a products list to store multiple product IDs and removed the single productId field. The current design uses the products list for post-product associations.
Q04 | Can an order contain more than one product? | orders carries a single product_id rather than a line item array. | If orders are single item, items bought together cannot be identified from orders and must be derived from carts or by grouping, which is weaker. | Platform | P1 | Done | The user can add multiple products to the cart and proceed with a single checkout. However, the products are not stored as multiple products under one order. Each product is converted into a separate order after checkout because products may have different delivery dates, different brand owners/sellers, shipping details, and fulfillment requirements. For example, if a customer purchases 5 products from different brands, the checkout can be completed together, but the system creates 5 separate orders, one for each product. This allows each order to be managed independently for delivery, seller/brand ownership, and fulfillment.
Q05 | Is influencerearnings intended to serve as the commission record? | The collection exists and is empty. There is no commissions collection. | Ranking opportunities for a promoter needs a commission rate per product. There is no rate term until this is settled. | Platform | P1 | Not started
Q06 | Which of the four order status fields defines a valid outcome? | order_status, payment_status, seller_delivery_status and buyer_approval_status are all present with no stated precedence. | The definition of a successful purchase, which every commerce model aims at and every quality threshold is set against. | Platform | P1 | Done | order_status === "Delivered" is the canonical success signal. It is written atomically by DeliveredBySeller (orderController.js:837) It is already used as the revenue floor in all dashboard analytics ($eq: "Delivered" in orderDashboardController.js:69) Every quality threshold, conversion rate, and ML label should be set against this field The other three fields should be treated as operational state only, not outcome signals One action item: Document order_status as the authoritative field in the order model and remove the ambiguity created by seller_delivery_status (either drop it or enforce a sync write whenever order_status changes).
Q07 | Is the current development data representative or purely test seed data? | Thirty populated collections, the largest holding 93 documents, activity concentrated across a few weeks. | Determines whether anything observed in the current data can inform design, or whether it can only confirm that fields exist. | Platform | P2 | Not started
Q08 | Will a separate database be provided for recommendation outputs? | Read access has been requested. Model outputs such as scores need somewhere to be written. | Scores cannot be persisted under a read-only credential. A writable namespace separate from application data is needed. | Platform | P2 | Done | Option A. ml_ prefixed collections in the same database, with a separate write scoped credential for the engine. Option B, a separate database, held in reserve if write load causes contention.
Q09 | What is the app launch target date? | Instrumentation additions have a lead time that only means something against a fixed date. | Whether the capture requirements land before launch or become a retrofit. A retrofit does not recover the traffic that arrived in the meantime. | Client | P1 | Needs discussion
Q10 | Does the ninety day window on userevents stay once the export exists, and when is the export scheduled? | The platform ML schema reference confirms a ninety day time to live on userevents. The app has not launched, so nothing of value has been lost. The requirement is that the export is live before go-live rather than that it starts today. | Nothing immediately. It becomes a permanent loss of behavioural history if the export is not in place before launch. Two open points: whether ninety days stays once the export runs, since a silent export failure would turn a pipeline fault into permanent loss, and whether ninety days covers any feature that reads events directly at serving time. | Platform | P2 | Done | Question 1: Does the 90-day TTL stay once the export exists? No — the TTL must be removed or extended once the export is live. Confirmed in the schema — userEventModel.js has a hard TTL index: userEventSchema.index({ timestamp: 1 }, { expireAfterSeconds: 7776000 }); // 90 days (userEventModel.js:23) If the export runs daily and the TTL stays at 90 days, documents older than 90 days are deleted by MongoDB regardless of whether the export succeeded. A single silent export failure would permanently destroy up to 90 days of behavioural history with no recovery path. The safe approach: once the export pipeline is confirmed healthy, either drop the TTL entirely (keep events permanently in the ML store, not MongoDB) or extend it to 180+ days as a safety buffer giving time to detect and recover from a failed export. Question 2: When should the export be scheduled? Before go-live — no data of value exists yet (app not launched, no real users). The requirement is that the export pipeline is proven live and confirmed working before launch day, not that it starts immediately today. Recommended schedule: Now: Export runs daily, confirmed working on seed/test data Before launch: Verified on first real user events At launch: TTL removal/extension applied, permanent history begins accumulating A daily export at a fixed off-peak time (e.g. 2 AM IST) copying all events older than 24 hours to the ML store is the standard approach. No export job or cron task exists in the codebase today — this is entirely new infrastructure work
Q11 | Which follow model is canonical, followers or follows? | Both model the same relationship with different schemas. The platform ML schema reference identifies this and recommends one is chosen, which is a platform decision rather than a data science one. | Candidate retrieval reads the follow graph directly. Building against the wrong one means the graph is read from a collection the application does not keep current, and the failure is silent rather than loud. | Platform | P1 | Done | The app writes to both. An ordinary follow goes to FollowModel. A follow request on a private account writes to followerModel with status requested, and moves to FollowModel on approval. The feed reads FollowModel exclusively, so retrieval reads FollowModel and sees all live follows. Block deletes FollowModel edges in both directions and writes status blocked to followerModel. Mute is not implemented anywhere.
Note on Q02. A yes to the entity alone is not a yes to the family that depends on it.
Brand match, model family M7, is the only family with no dedicated fallback. It is the sole family serving Engine C, and Engine C does not function without it. It is blocked on this decision rather than on data, which means no amount of traffic clears the block.
A campaign entity on its own unblocks only half of it. M7's first form ranks promoters by the promoter score against a campaign's category and region, and that needs the entity as a query object and nothing else. Its learned form ranks promoters by predicted campaign outcome, and that needs the outcome records: promoter invitation, acceptance, completion or withdrawal, and the results delivered.
The failure mode to watch for is a partial yes. If the entity is built but the lifecycle and invitation records are not, M7 is unblocked for its rules form and permanently blocked for its learned form, and it will read as a yes to everyone involved. The answer to Q02 should therefore state both parts separately.
Timing changes the cost rather than the answer. Before launch, M7 joins Wave 1A but adds entity, lifecycle states, brand surfaces and invitation records to the launch build, which is not a field addition. After launch, it joins Wave 1B, and the campaign data clock starts from the entity's creation date rather than from launch. Never, and Engine C leaves Wave 1, which should be recorded as a scope reduction rather than left as an unanswered question.
One quality caveat regardless of timing. At launch the promoter score is heavily pulled toward the category average, because almost no promoter has enough evidence behind them. M7's ranking will therefore be flat and low confidence, and should be shown to brands with confidence bands rather than as a clean ordered list. A list implies a precision that is not there, and getting that wrong early costs more trust than not shipping the feature would.

## Capture register
Capture register ¦ What the app must record from launch day (PT-05)
The recommendation engine learns from what it observes. Anything not recorded from launch day cannot be reconstructed afterwards, and the learning period for whatever depends on it starts from the date it is added rather than from launch. Three responses are needed: an accept or defer decision on each of the twelve events in section 1, a status on each of the fifty-eight fields in section 2, and a status on each of the eight data model changes in section 3. Seventy-eight rows in total.
Priority meanings. Blocking: the learned models cannot be built at all without it, and there is no workaround. Important: they can be built, but with noticeably lower quality or a longer wait for enough data. Useful: improves quality and can follow after launch without penalty.
Section 1. The twelve events. Set an accept or defer decision on every row.
Decide here whether the event is being emitted at all, before working through its fields below. An event accepted with several of its fields deferred is usually a mistake rather than a decision, and the Field responses column is there to make that visible. It fills in automatically from section 2, so there is nothing to type in it.
ID | Event name | Fired when |  |  | Priority | Why it is needed | Where it comes from | How to check it is right | Event decision | Field responses, calculated | Platform team notes
E1 | recommendation_request | Any surface asks the backend for a list of items to show |  |  | Blocking | Creates the request identifier that ties everything else together. Without it, no other event can be linked to a decision. | Recommendation service, server side. Emitted as the recommendation API builds its response. Not an endpoint of its own. | No endpoint today. Confirm the event appears once per served list, and that the identifier it carries is the one returned to the client. | Accepted | 7 of 7 answered, 1 deferred | API endpoint: /dashboard-feed (/feed/dashboard-feed) Request: Sends user_id, limit, isBusinessAccount, page, and refreshSeed. refreshSeed is generated by Flutter on pull-to-refresh and acts as a feed variety/shuffle signal. The backend uses it to vary the ordering of posts with similar recommendation scores, helping prevent the user from receiving the exact same feed order after every refresh. Validation: Confirm that changing refreshSeed can produce a different ordering for otherwise similar-ranked posts, while the overall recommendation logic remains valid.
E2 | recommendation_impression | An item actually appears on the user's screen |  |  | Blocking | Records what was shown and in what position. This is the comparison the engine learns from, more than the clicks themselves. | Client, Flutter app. Fires from the list widget's visibility callback when an item scrolls into view. No endpoint exists for it. | Scroll a feed, then confirm one event per item that entered the screen and none for items never reached. | Accepted | 8 of 8 answered, 0 deferred | VisibilityDetector package is already installed and in use in the feed widgets (feed_post_media.dart:144, media_post.dart:134). However the onVisibilityChanged callbacks are only used to control video playback (pause/resume) — no API call is fired. The hook point already exists; we just need to add the impression API call inside onVisibilityChanged when visibleFraction > 0.5. No new package needed. No new widget wrapping needed. Just add the API call in the existing callback.
E3 | recommendation_click | User taps an item that was shown |  |  | Blocking | The positive signal. Only meaningful when paired with the impressions that were not clicked. | Client, on tap. Fires alongside the navigation call the tap already triggers. | Tap an item and confirm the event carries the same request identifier as the impression for that item. | Accepted | 4 of 4 answered, 0 deferred | There is no single tap handler on the feed card that navigates to the post detail screen — taps are handled per-zone (like, comment, share, bookmark, more options). There is no GestureDetector.onTap wrapping the whole card that navigates to post detail. To capture recommendation_click, a card-level onTap needs to be added (or the existing navigation call located and instrumented). The click event must carry the same request_id as the impression for that post — so request_id (F01) must be solved first before this event is meaningful.
E4 | add_to_cart | User adds a product to cart |  |  | Important | An intermediate signal that arrives far more often than purchases, which matters while order volume is low. | Backend, existing cart endpoint. Emitted after the cart write succeeds. | Endpoint exists, event does not. Add to cart and confirm the event fires with the request identifier threaded through from the client. | Accepted | 3 of 3 answered, 0 deferred | Two separate APIs fire on add-to-cart — both exist, but they are not linked. 1. Cart write → POST /cart (commonRouter.js:209) Saves the cart item to DB via cartModel. This is the actual cart write the spec refers to. 2. Engagement event → POST /engagement/action with event: "add_to_cart" (product_details_screen.dart:2428) Fired from Flutter after the cart write succeeds. Increments addToCartCount on the post and fires a PostEvent for influencer analytics. What's missing: Neither call carries a request_id — so the add_to_cart event cannot be traced back to the feed recommendation that surfaced the product. The engagement event body only has post_id, user_id, event, product_id. The request_id from the original recommendation_request (F01) must be stored client-side and threaded through here to make this signal meaningful for the recommendation engine.
E5 | order_placed | Order is created |  |  | Blocking | The primary commercial outcome the product ranker optimises for. | Backend, existing order creation endpoint. Emitted after the order document is written. | Endpoint exists, event does not. Place an order and confirm one event per order. | Accepted | 7 of 7 answered, 0 deferred | Endpoint exists (POST /order) and the order document is written correctly. After the save, a PostEvent with event_type: 'purchase' is fired for influencer analytics (orderController.js:374) — but this is not the same as an order_placed recommendation event. The PostEvent only fires if a post_id is linked to the order; orders that arrive without a post_id fall back to a product lookup which may also fail silently — meaning purchases not traced to a post produce no event at all. A dedicated order_placed event must be emitted unconditionally after savedOrder is written, carrying order_id, request_id, line_items, order_value, and server_ts — regardless of whether a post_id is present.
E6 | order_state_changed | Order moves to delivered, cancelled, returned or refunded |  |  | Blocking | Without terminal states the engine learns to promote items that get bought and sent back. | Backend, every place an order status is written. Not one endpoint: includes admin actions and scheduled jobs, which is why it is the easiest to half implement. | Writes exist, event does not, and the return and refund states themselves do not exist yet. See D1 and D2. Search the codebase for every write to order status, including jobs, and confirm each emits. | Accepted | 4 of 4 answered, 0 deferred | Status writes exist across 5 separate endpoints — confirmOrderBySeller (→ Accepted), confirmOrderByUser (→ Confirmed), shippedOrderBySeller (→ Shipped), DeliveredBySeller (→ Delivered), cancelOrderByUser / cancelOrderBySeller / rejectOrderByUser (→ Cancelled / Rejected). Each writes order_status to the DB and pushes a tracking_info entry, but none fire a structured analytics event — no PostEvent, no log, no webhook for state changes. Additionally, Returned and Refunded states do not exist at all in the codebase (only Pending → Accepted → Confirmed → Shipped → Delivered / Cancelled / Rejected). Each status-write endpoint needs to emit an order_state_changed event with {order_id, prev_status, new_status, server_ts} after the save succeeds.
E7 | payment_state_changed | Payment settles, fails or is charged back |  |  | Important | Separates a completed sale from an abandoned one. Failed payments otherwise count as successes. | Backend, payment gateway webhook handler rather than a user facing call. | Webhook exists, event does not. Confirm settle, fail and chargeback each emit. | Needs discussion | 3 of 3 answered, 0 deferred | Razorpay is integrated (razorpayInstance in adminService.js:123) and an order is created via razorpayInstance.orders.create(). However no webhook handler exists — there is no endpoint to receive Razorpay callbacks for payment.captured, payment.failed, or payment.dispute.created (chargeback). Payment success/failure is only checked client-side via a flag (payment.success). The order's payment_status field exists on the model but is only updated manually via changePaymentBySeller. Settle, fail and chargeback states are never captured automatically. A Razorpay webhook endpoint must be created to emit payment_state_changed for each of these three transitions.
E8 | commission_state_changed | Commission is attributed, confirmed or reversed |  |  | Blocking | The outcome signal for promoter matching and the promoter score. | Backend, commission attribution. Likely a job rather than a request. | Attribution exists, reversal may not. Confirm all three transitions emit, not only the first. | Accepted | 6 of 6 answered, 0 deferred | InfluencerEarning model exists (influencerAnalyticsModel.js:65) and an earning record is auto-created on purchase event with status: "pending". Status enum has three values: pending → approved → paid. However only the first transition fires (record creation at purchase time) — there is no code anywhere that moves a record from pending to approved or approved to paid, and no event is emitted on any transition. Reversal does not exist at all — there is no reversed / cancelled status on the model. All three transitions (attributed, confirmed, reversed) need dedicated handlers that emit a commission_state_changed event.
E9 | social_interaction | Like, save, share, repost or follow |  |  | Important | Engagement signals for the feed ranker. Needs to be an event with a timestamp, not only a counter on the item. | Backend, the existing like, save, share, repost and follow endpoints. Today these update a counter; the event adds who and when. | Endpoints exist, events do not. Confirm each of the five actions emits with a timestamp and an actor. | Accepted | 5 of 5 answered, 0 deferred | All five actions have endpoints — like (/engagement/like), save (/engagement/action → save), share (/engagement/action → share), repost (stored as postType: "repost" on post creation), follow (/follow/toggle). Each increments a counter on the post. PostEvent is fired for like, save, and share with {influencer_id, post_id, event_type, user_id} — but no timestamp is explicitly set (relies on created_at default) and follow and repost fire no PostEvent at all. The actor (who performed the action) is present as user_id in like/save/share but completely absent from follow and repost events. All five need a structured social_interaction event with {actor_id, target_id, action, post_id, timestamp}
E10 | opportunity_state_changed | Promoter accepts, completes, withdraws from or lets an opportunity expire |  |  | Blocking | The outcome signal for promoter to opportunity matching. Acceptance alone is not enough. | Backend, promoter opportunity flow. Accept and complete come from endpoints, expiry comes from a job. | Confirm expiry emits as well as accept and complete. Expiry is the one that comes from a job and is usually missed. | Deferred | 5 of 5 answered, 1 deferred | No opportunity / promoter flow exists anywhere in the codebase — no model, no router, no controller for promoter opportunities (accept, complete, withdraw, expire). The spec mentions accept and complete come from endpoints and expiry from a job. This is entirely unbuilt. Needs discussion to define what an "opportunity" is in SOCO's context before any implementation can begin.
E11 | search_performed | User runs a search |  |  | Useful | Direct statement of intent, and the strongest available signal for a new user with no history. | Backend, existing search endpoint. | Endpoint exists, event does not. Run a search and confirm one event with the query and the result count. | Accepted | 4 of 4 answered, 0 deferred | Search endpoint exists at GET /search (searchRouter.js:8) via unifiedSearch. The response already echoes back query and returns results for people, products, places. However no search_performed event is fired — no analytics log, no PostEvent, nothing stored. Result counts are available from each sub-search result but are not totalled or logged. Need to emit a search_performed event after the search resolves with {user_id, query, type, result_count, server_ts} — can be fire-and-forget so it doesn't affect response latency.
E12 | identity_stitched | Anonymous activity is linked to an account at login |  |  | Important | Preserves pre-login browsing. Without it, every new user looks like they have no history. | Backend, inside the login flow when an anonymous identifier is linked to an account. No endpoint of its own. | Log in from a device that browsed anonymously and confirm one event linking the two identifiers. | Needs discussion | 3 of 3 answered, 0 deferred | No anonymous identity concept exists in the codebase — there is no device_id, guest_id, or anonymous_id stored anywhere. The login endpoint (POST /login) authenticates a user but does not receive or link any pre-login anonymous identifier. Flutter does not generate or pass a guest session token before login. Both the anonymous identifier on the client side and the stitch event on the backend are missing entirely. This requires a product decision: Flutter must generate a persistent anonymous ID before login, pass it at login time, and the backend must emit identity_stitched linking {anonymous_id, user_id} once authentication succeeds.
Section 2. The fifty-eight fields. Set the Current status on every row.
Req ref meanings, so the column reads without needing anything else. R1 a request identifier on every recommendation request. R2 impressions logged with position and the candidate set they came from. R3 a policy stamp on every served list. R4 outcomes published again when they reach a final state. R5 a small randomised slice of traffic, see section 4. R6 one canonical identity and stable join keys. R7 time discipline on timestamps.
ID | Event | Field name | Type | Example value | Priority | Req ref | Why this field is needed | Where the value comes from | Current status | Platform team notes |  | How to check it is right
F01 | recommendation_request | request_id | string | req_8f2a1c | Blocking | R1 | The single identifier that links a request to everything that follows from it | Generated by the recommendation service when the list is built, returned in the API response, then echoed back by the client on every event that follows. | Will add | No request ID exists. Must be generated server-side and returned in response + logged. |  | Sample a hundred child events and join back to the request. Zero orphans, and no nulls.
F02 | recommendation_request | surface | enum | feed | Blocking | R1 | Which screen asked. Each surface is ranked by a different model | Set by the client on the request, from the screen making the call. No lookup and no derivation. | Partially captured | Exists as feedType in request body and meta response. Values match but field name differs — needs rename/alias to surface. |  | Values fall only in the agreed set. No free text, no nulls, and the value is set at the call rather than inferred afterwards.
F03 | recommendation_request | user_id | string | usr_4471 | Blocking | R6 | Who the request was for | The authenticated user on the request context. | Already captured | Same name, sent in request body, used server-side. No change needed. |  | Populated on every event from a logged in session, and resolves to a user document.
F04 | recommendation_request | session_id | string | ses_9931 | Important | R6 | Groups activity within one visit | The session identifier the app already holds. | Deferred | Flutter has no session token concept currently. Needs agreement on whether to use app session, auth token, or generate a new one. |  | Stable across a visit and changes between visits.
F05 | recommendation_request | candidate_ids | array | [prd_1, prd_2, ...] | Blocking | R2 | What was available to choose from, including items not shown | The shortlist the engine assembled before ranking. Held in the service and not returned to the client. | Partially captured | Shortlist exists internally as allPosts before ranking but IDs are never logged or returned. Need to expose allPosts.map(p => p._id) in the response/log. |  | Length is greater than the number of items actually shown. If the two are equal, only shown items are being logged and the field is not doing its job.
F06 | recommendation_request | policy_id | string | wave1a_v3 | Blocking | R3 | Which version of the ranking logic produced this list | The running configuration version of the ranking logic, set by the service. | Will add | Scoring formula is hardcoded with no version identifier. Need to define a constant like wave1a_v1 and attach it to the response meta. |  | Changes when the ranking configuration changes, and the change is timestamped.
F07 | recommendation_request | server_ts | datetime | 2026-11-04T09:15:22.140Z | Blocking | R7 | When the decision was made, in UTC | Backend system clock at the moment the action was handled. | Will add | Server clock is available but not stamped on response. Easy to add server_ts: new Date().toISOString() to the meta block. |  | UTC, ISO 8601, millisecond precision, and not equal to the time the event was ingested.
F08 | recommendation_impression | request_id | string | req_8f2a1c | Blocking | R1 | Links the impression back to the request | Generated by the recommendation service when the list is built, returned in the API response, then echoed back by the client on every event that follows. | Will add | Not generated anywhere today. The feed response has no request_id field. Flutter receives posts but no identifier to attach to impressions. Blocked on F01 — once the backend stamps request_id on the feed response, Flutter must store it and echo it back with every impression event for the posts in that response. |  | Sample a hundred child events and join back to the request. Zero orphans, and no nulls.
F09 | recommendation_impression | item_id | string | prd_5512 | Blocking | R2 | Which item was shown | The identifier of the item the client rendered. | Already captured | Each post has an id (MongoDB _id) available on the FeedPost / PostModel in Flutter. It is the natural item_id. Already available in the VisibilityDetector callback via widget.post.id (feed_post_media.dart:145). Just needs to be included in the event payload. |  | Resolves to a product, post, promoter or brand document.
F10 | recommendation_impression | item_type | enum | product | Blocking | R2 | Product, promotion, promoter or brand | Set by the client from the list it is rendering. | Partially captured | PostModel has isProductPost (bool), postType (string), and postTypeDetailed on the Flutter model — enough to derive the item type. However no standardised item_type enum (product, promotion, promoter, brand) is mapped or sent to the backend. A mapping function from the existing flags to the spec enum needs to be added client-side before firing the event. |  | Values fall only in the agreed set.
F11 | recommendation_impression | position | integer | 4 | Blocking | R2 | Where it appeared in the list. Items at the top get clicked far more regardless of quality, and without this the engine cannot tell the difference | The index of the item in the list the client rendered, counting from one. | Will add | The SliverChildBuilderDelegate in feed_content.dart already has the list index available at build time (feed_content.dart:196). However index is not passed down to the post card or the VisibilityDetector. It needs to be threaded through SocoPostCard → FeedPostMedia so the impression event can include the 0-based position. |  | Integers from one upward, no gaps within a single request, and click rate falls as position rises.
F12 | recommendation_impression | viewport_entered | boolean | true | Blocking | R2 | Whether the user actually scrolled far enough to see it | The visibility callback on the list widget. | Partially captured | VisibilityDetector is already installed and onVisibilityChanged fires at visibleFraction > 0.3 (carousel) and >= 0.5 (video) (feed_post_media.dart:147, 401). The callback exists but only controls video playback — no API call fires. The hook is there; just need to add the impression event call with viewport_entered: true when nowVisible becomes true for the first time per post. |  | Both true and false appear. If every row is true, items that were never seen are being logged as impressions.
F13 | recommendation_impression | dwell_ms | integer | 2400 | Important | R2 | How long it stayed on screen. A weak signal on its own, useful in combination | Time between the item entering and leaving the viewport, measured on the client. | Will add | No dwell timing exists. The onVisibilityChanged callback knows when a post enters (nowVisible = true) and leaves (nowVisible = false) the viewport, but no _enterTime is recorded and no duration is calculated. Need to stamp DateTime.now() on enter and compute the difference on leave, then include dwell_ms in the impression event. |  | Positive, and not identical across items in one request.
F14 | recommendation_impression | is_exploration | boolean | false | Blocking | R5 | Marks the small randomised slice of traffic. See the Exploration slice sheet | Returned by the service on the response and echoed by the client. Not computed on the client. | Will add | No exploration slice concept exists — the backend does not mark any posts as exploration traffic and the feed response has no is_exploration flag. The spec says it is returned by the service on the response and echoed back by the client. Needs to be added to the feed scoring logic as a small randomised slice, flagged on the post objects in the response meta or per-post, and echoed back by Flutter with the impression. |  | The share of true rows matches the agreed percentage within about one point.
F15 | recommendation_impression | client_ts | datetime | 2026-11-04T14:45:22+05:30 | Important | R7 | Device time with offset, kept separate from server time | Device clock with its timezone offset. | Will add | Flutter never sends a client-side timestamp with any event. DateTime.now() with timezone offset is available in Dart as DateTime.now().toIso8601String(). Needs to be stamped at the moment the VisibilityDetector callback fires and included in the impression payload — kept separate from server_ts so clock skew between device and server can be detected. |  | Carries a timezone offset and differs from server_ts. Never overwritten by server time.
F16 | recommendation_click | request_id | string | req_8f2a1c | Blocking | R1 | Links the click to what else was on screen at the time | Generated by the recommendation service when the list is built, returned in the API response, then echoed back by the client on every event that follows. | Will add | Same as F08 — no request_id exists on the feed response today. Flutter has no value to echo back on tap. Blocked on F01. Once the feed response carries request_id, Flutter must store it per-page and include it alongside the item_id when the card-level tap fires. |  | Sample a hundred child events and join back to the request. Zero orphans, and no nulls.
F17 | recommendation_click | item_id | string | prd_5512 | Blocking | R4 | What was chosen | The identifier of the item the client rendered. | Will add | post.id is available at the tap site — the same id used for the impression (F09). However there is no card-level onTap that navigates to the post detail screen today (confirmed in E3 — taps are zone-split: like, comment, share, more options each have their own GestureDetector). A wrapping card tap handler must be added, and item_id included in the click event it fires. |  | Resolves to a product, post, promoter or brand document.
F18 | recommendation_click | position | integer | 4 | Blocking | R2 | Position of the clicked item | The index of the item in the list the client rendered, counting from one. | Will add | Same blocker as F11 — the list index is available in SliverChildBuilderDelegate (feed_content.dart:196) but is not passed down to the card. Once index is threaded through to the card tap handler (same work as F11), it becomes position here with no extra effort. F11 and F18 can be solved together. |  | Integers from one upward, no gaps within a single request, and click rate falls as position rises.
F19 | recommendation_click | server_ts | datetime | 2026-11-04T09:15:31.002Z | Blocking | R7 | When the click happened | Backend system clock at the moment the action was handled. | Will add | No click event endpoint exists today so nothing is timestamped server-side. Once the recommendation_click endpoint is built, server_ts: new Date().toISOString() is stamped at the moment the request is handled — same pattern as all other server_ts fields. No special work needed beyond creating the endpoint. |  | UTC, ISO 8601, millisecond precision, and not equal to the time the event was ingested.
F20 | add_to_cart | request_id | string | req_8f2a1c | Important | R4 | Links the intent back to what prompted it | Generated by the recommendation service when the list is built, returned in the API response, then echoed back by the client on every event that follows. | Will add | Not present in the add_to_cart engagement event body. The call at transaction_provider.dart:336 sends only post_id, event, product_id, user_id. The request_id from the original feed recommendation must be stored client-side when the feed loads and threaded through here. Depends on F01 being solved first. |  | Sample a hundred child events and join back to the request. Zero orphans, and no nulls.
F21 | add_to_cart | product_id | string | prd_5512 | Important | R4 | Which product | The product on the cart write. | Already captured | Sent correctly in the engagement event body as 'product_id': productId at transaction_provider.dart:339. Also stored on the /cart write in cartModel. No change needed. |  | Resolves to a product document.
F22 | add_to_cart | quantity | integer | 2 | Useful | R4 | Strength of intent | The quantity on the cart write. | Partially captured | qty is sent to the /cart write and saved in cartModel. However it is not included in the engagement event (/engagement/action body). Additionally, the analytics event is only fired when result.quantity == 1 (first add only — transaction_provider.dart:332), meaning repeat adds or quantity increments are silently skipped. Need to add quantity to the engagement body and decide whether to track all cart updates or first-add only. |  | Positive integer.
F23 | order_placed | order_id | string | ord_2210 | Blocking | R4 | Order identifier | The order document identifier. | Already captured | savedOrder._id is available immediately after the order document is saved in createOrder (orderController.js:318) and returned in the response. No change needed. |  | Resolves to an order document, and reconciles one to one with orders created in the same window.
F24 | order_placed | request_id | string | req_8f2a1c | Blocking | R4 | Which recommendation led to the order. This is the single most valuable link in the whole list | Generated by the recommendation service when the list is built, returned in the API response, then echoed back by the client on every event that follows. | Will add | Not present anywhere in the order flow. createOrder body accepts post_id but no request_id. Must be threaded from Flutter at order creation time and stored on the order document. Depends on F01. |  | Sample a hundred child events and join back to the request. Zero orphans, and no nulls.
F25 | order_placed | line_items | array | [{product_id, qty, price}] | Blocking | R4 | Every product on the order. A single product_id per order prevents any basket or co-purchase analysis | The basket contents. Blocked on D3, since orders carry one product identifier today. | Partially captured | Current order is single-product only — product_id, quantity, and total_price are saved on the order document. No line_items array structure exists because the system does not support multi-product orders yet. Cart is stored separately in cartModel but never consolidated into a single order write. A line_items: [{product_id, qty, price}] shape needs to be added. |  | Every product in the basket appears. A single item where the basket held three means D3 is not done.
F26 | order_placed | promoter_id | string | pro_0087 | Blocking | R4 | Which promoter, if the order came through a promotion | The referral attribution held on the order. | Partially captured | Promo code is stored as promoCode snapshot on the order (orderController.js:314) containing promoId, discountApplied, etc. However there is no promoter_id / referral attribution field — no concept of which influencer/user the promo came from. Needs a promoter_id field added to the promo snapshot. |  | Populated on referred orders and empty on direct ones. Not null on all rows, which is the current defect.
F27 | order_placed | order_value | decimal | 2499.00 | Blocking | R4 | Value, for ranking by revenue rather than click count | The order total. | Already captured | Saved as total_price (post-discount) and base_price (pre-discount) on the order document. Also returned in response via buildPricingSummary. Field name differs — spec calls it order_value, codebase uses total_price. |  | Matches the order total on the operational record.
F28 | order_placed | server_ts | datetime | 2026-11-04T09:22:10.500Z | Blocking | R7 | When the order was placed | Backend system clock at the moment the action was handled. | Will add | Not explicitly stamped on the order_placed event. The order document has createdAt via Mongoose timestamps, but it is not included in the response or fired as a named event field. Easy to add as server_ts: new Date().toISOString() in the response. |  | UTC, ISO 8601, millisecond precision, and not equal to the time the event was ingested.
F29 | order_state_changed | order_id | string | ord_2210 | Blocking | R4 | Which order changed | The order document identifier. | Already captured | order._id is available in every status-write handler (Accepted, Confirmed, Shipped, Delivered, Cancelled, Rejected). It is returned in all responses. No change needed — just needs to be included when the structured order_state_changed event is emitted. |  | Resolves to an order document, and reconciles one to one with orders created in the same window.
F30 | order_state_changed | new_state | enum | returned | Blocking | R4 | One canonical state field. Four parallel status fields with no defined precedence cannot be used as an outcome | The status value being written. Which field is authoritative is Q06 and D2. | Partially captured | Status is written to the order document but split across four parallel fields — order_status, seller_review_status, buyer_approval_status, and is_Delivered/is_Shipped — with no defined precedence between them. Also the current states are: Pending → Accepted → Confirmed → Shipped → Delivered / Cancelled / Rejected. Returned and Refunded states do not exist at all. The spec requires one canonical new_state enum field. All four parallel fields must be collapsed into one authoritative field before this can be trusted. |  | Every terminal state appears at least once. Reconcile counts by state against the orders collection.
F31 | order_state_changed | reason_code | string | size_mismatch | Important | R4 | Why. Separates a product problem from a delivery problem | The cancellation or return reason, where one is captured. | Partially captured | Cancel reason is captured in two separate fields — cancel_reason_by_buyer (from cancelOrderByUser) and cancel_reason + cancel_category (from cancelOrderBySeller). Reject reason stored separately as reject_reason_by_buyer. No reason is captured for Shipped or Delivered transitions. The fields exist but are inconsistently named across endpoints and there is no standardised reason_code enum — free-text strings are stored instead of a controlled vocabulary (e.g. size_mismatch, delivery_failed). |  | Populated where a reason exists. Blank is acceptable, a wrong default is not.
F32 | order_state_changed | state_ts | datetime | 2026-11-09T11:02:00Z | Blocking | R7 | When the state changed, not when the record was written | Backend clock at the moment the state changed, not when the row was read. | Partially captured | Each tracking_info push includes a timestamp: new Date() at the moment of the status write (orderController.js:489, 593, 764, 840). The timestamp is correct but buried inside the tracking_info array — not surfaced as a top-level state_ts field on the event. Needs to be promoted to a named field when the order_state_changed event is emitted. |  | Ordered correctly against the creation time, and reflects when the change happened.
F33 | payment_state_changed | order_id | string | ord_2210 | Important | R4 | Which order | The order document identifier. | Already captured | order_id is stored on the order document and on InfluencerEarning. Razorpay order creation also receives an orderId in additionalData (orderController.js:400). Available to attach to the event once the webhook handler is built. No change needed to the data — only to the event emission. |  | Resolves to an order document, and reconciles one to one with orders created in the same window.
F34 | payment_state_changed | new_state | enum | settled | Important | R4 | Settled, failed or charged back | The status value being written. Which field is authoritative is Q06 and D2. | Will add | No webhook handler exists so no state is captured at all today. The three states the spec requires — settled, failed, charged_back — map to Razorpay webhook events payment.captured, payment.failed, payment.dispute.created. Currently only payment_status: "Completed" is written manually by the seller via changePaymentBySeller — this covers only the settled path and only when the seller acts, not automatically. All three states need the webhook handler to write them and emit the event. |  | Every terminal state appears at least once. Reconcile counts by state against the orders collection.
F35 | payment_state_changed | state_ts | datetime | 2026-11-04T09:23:40Z | Important | R7 | When | Backend clock at the moment the state changed, not when the row was read. | Will add | No payment webhook exists so no timestamp is captured at the moment the payment settles, fails, or is charged back. The only existing timestamp is the tracking_info push on changePaymentBySeller which is manual and server-clock at the time the seller clicks — not the actual payment gateway event time. Razorpay webhooks carry a created_at Unix timestamp on the event payload which should be used as state_ts rather than new Date() to reflect when Razorpay processed the state, not when our server handled it. |  | Ordered correctly against the creation time, and reflects when the change happened.
F36 | commission_state_changed | commission_id | string | com_7781 | Blocking | R4 | Commission record identifier | The commission record identifier. | Already captured | InfluencerEarning document is created per order. Its _id (MongoDB ObjectId) serves as the commission record identifier. Not currently exposed as commission_id in any event or response — just needs to be named commission_id when the commission_state_changed event is emitted. |  | Resolves to a commission record.
F37 | commission_state_changed | promoter_id | string | pro_0087 | Blocking | R4 | Which promoter earned it | The referral attribution held on the order. | Partially captured | Stored as influencer_id on the InfluencerEarning record (influencerAnalyticsModel.js:66). Field exists and is set correctly at record creation. Field name differs — spec calls it promoter_id, model uses influencer_id. No data change needed, just alias the field name in the event payload. |  | Populated on referred orders and empty on direct ones. Not null on all rows, which is the current defect.
F38 | commission_state_changed | order_id | string | ord_2210 | Blocking | R4 | Which order it came from | The order document identifier. | Already captured | order_id is a required field on InfluencerEarning (influencerAnalyticsModel.js:67) and is set at creation. Unique index enforces one earning record per order. Ready to include in the event as-is. |  | Resolves to an order document, and reconciles one to one with orders created in the same window.
F39 | commission_state_changed | new_state | enum | confirmed | Blocking | R4 | Attributed, confirmed or reversed | The status value being written. Which field is authoritative is Q06 and D2. | Partially captured | status enum exists with pending → approved → paid. However reversed state does not exist — the enum has no cancelled or reversed value, so order cancellations or refunds cannot be reflected. Also no code transitions a record from pending to approved or approved to paid — only pending is ever written today. Need to add reversed to the enum and build the handlers for all three transitions, each emitting the event. |  | Every terminal state appears at least once. Reconcile counts by state against the orders collection.
F40 | commission_state_changed | amount | decimal | 249.90 | Blocking | R4 | Value earned | The commission value on the record. | Already captured | Stored as commission_amount on the record (influencerAnalyticsModel.js:73), calculated as base_amount × commission_rate (10%) at creation time. Field name differs — spec calls it amount. Value is correct and ready to include in the event payload. |  | Matches the commission on the operational record.
F41 | commission_state_changed | state_ts | datetime | 2026-11-20T00:00:00Z | Blocking | R7 | When | Backend clock at the moment the state changed, not when the row was read. | Will add | Only created_at exists on the record — the timestamp of the initial pending creation. There is no per-transition timestamp stored when status moves to approved, paid, or reversed. payout_date captures when payment is made but is never set by any current code. Need to add a state_ts field that is stamped with new Date() at each status transition and included in the event. |  | Ordered correctly against the creation time, and reflects when the change happened.
F42 | social_interaction | user_id | string | usr_4471 | Important | R4 | Who acted | The authenticated user on the request context. | Partially captured | Present as user_id in PostEvent for like, save, share (postEngagementController.js:127). However follow only stores follower_id and following_id in FollowModel — no PostEvent is fired, so the actor is never recorded in analytics. Repost creates a new post document with repostDetails.originalUserId but again no analytics event is fired. Actor field is inconsistent across all five actions. |  | Populated on every event from a logged in session, and resolves to a user document.
F43 | social_interaction | target_id | string | pst_3390 | Important | R4 | What they acted on | The post, product or user the action was performed on. | Partially captured | For like/save/share, post_id serves as the target and is captured in PostEvent. For follow, the target is the following_id (user being followed) — exists in FollowModel but not in any analytics event. For repost, the target is repostDetails.originalPostId on the new post document — also not in any analytics event. A unified target_id field covering post, user, and product targets does not exist. |  | Resolves to the item acted on.
F44 | social_interaction | action | enum | save | Important | R4 | Like, save, share, repost or follow | Which of the five interaction handlers fired. | Partially captured | event_type in PostEvent covers like, save, share — three of the five. follow and repost fire no event at all so their action is never recorded in analytics. The field name also differs — spec calls it action, model uses event_type. All five need to emit into the same event with a consistent action enum field. |  | All five actions appear across a sample.
F45 | social_interaction | request_id | string | req_8f2a1c | Important | R1 | Where they saw it, if it came from a recommended list | Generated by the recommendation service when the list is built, returned in the API response, then echoed back by the client on every event that follows. | Will add | Not present in any social interaction handler. None of the five endpoints (like, save, share, follow, repost) receive or store a request_id. This field links the action back to the feed recommendation that surfaced the content — requires Flutter to pass the request_id from the feed response alongside the action. Depends on F01 being solved first. |  | Sample a hundred child events and join back to the request. Zero orphans, and no nulls.
F46 | social_interaction | server_ts | datetime | 2026-11-04T09:16:05Z | Important | R7 | When. A counter on the post records that 340 people liked it, but not who or when, which makes it unusable as a learning signal | Backend system clock at the moment the action was handled. | Partially captured | PostEvent has a created_at field that defaults to now at insert time (influencerAnalyticsModel.js:30) — so like/save/share have an implicit timestamp. However it is never returned in any response or named server_ts. Follow timestamp exists in FollowModel as createdAt (Mongoose auto). Repost has timestamp on the post document. None are surfaced as a named server_ts field on a unified analytics event — and follow/repost have no analytics event at all to attach it to. |  | UTC, ISO 8601, millisecond precision, and not equal to the time the event was ingested.
F47 | opportunity_state_changed | opportunity_id | string | opp_1120 | Blocking | R4 | Which opportunity | The opportunity record identifier. | Will add | No opportunity model or record exists anywhere in the codebase. There is no collection, schema, or identifier for promoter opportunities. Needs a new OpportunityModel with an _id that becomes opportunity_id. |  | Resolves to an opportunity record.
F48 | opportunity_state_changed | promoter_id | string | pro_0087 | Blocking | R4 | Which promoter | The referral attribution held on the order. | Will add | InfluencerEarning has influencer_id which is the closest concept — but that is a commission record, not an opportunity record. No promoter is linked to an opportunity today because opportunities don't exist. Once the model is built, promoter_id maps to the influencer/promoter's user _id. |  | Populated on referred orders and empty on direct ones. Not null on all rows, which is the current defect.
F49 | opportunity_state_changed | campaign_id | string | cmp_0031 | Blocking | R6 | Which campaign it belongs to. Requires a campaign entity to exist, see Data model changes | The campaign the opportunity belongs to. Blocked on Q02, since no campaign entity exists. | Deferred | No campaign entity exists in the codebase — no model, no router, no controller. The spec itself flags this as blocked on a data model change ("Requires a campaign entity to exist, see Data model changes"). campaign_id cannot be captured until the campaign model is designed and built. Blocked on a separate data model decision before opportunity_state_changed can be fully implemented. |  | Blank until Q02 is answered. Do not populate it with a promo code.
F50 | opportunity_state_changed | new_state | enum | completed | Blocking | R4 | Accepted, completed, withdrawn or expired | The status value being written. Which field is authoritative is Q06 and D2. | Will add | No opportunity state machine exists. The four states the spec requires — accepted, completed, withdrawn, expired — are entirely unbuilt. Accept and complete need REST endpoint handlers; withdrawn needs either an endpoint or a Flutter-triggered cancel; expired needs a scheduled job (cron) that scans open opportunities past their deadline and transitions them. All four transitions must emit the event. |  | Every terminal state appears at least once. Reconcile counts by state against the orders collection.
F51 | opportunity_state_changed | state_ts | datetime | 2026-11-12T08:00:00Z | Blocking | R7 | When | Backend clock at the moment the state changed, not when the row was read. | Will add | No opportunity record exists to timestamp. Once the model and state transitions are built, state_ts should be stamped as new Date() at the moment each transition write succeeds — not updatedAt from Mongoose (which reflects the last field write, not necessarily the state change). A dedicated state_changed_at field on the model is the clean approach. |  | Ordered correctly against the creation time, and reflects when the change happened.
F52 | search_performed | user_id | string | usr_4471 | Useful | R4 | Who searched | The authenticated user on the request context. | Will add | unifiedSearch (searchController.js:344) does not receive or read a user_id — the endpoint is unauthenticated and takes only q, type, page, limit, and location params. No auth middleware attaches the caller's identity. user_id must be added as a query param (or auth header) and passed into the search_performed event when emitted. |  | Populated on every event from a logged in session, and resolves to a user document.
F53 | search_performed | query_text | string | cotton kurta | Useful | R4 | What they typed. The clearest statement of intent available | The raw search string as typed. | Will add | The raw query string is available as req.query.q and is already echoed back in the response as query. Not stored or logged anywhere. Ready to include in the search_performed event immediately — no data change needed, just emit it. |  | Present and not truncated.
F54 | search_performed | result_count | integer | 23 | Useful | R4 | Zero-result searches show unmet demand | The number of results returned for that search. | Will add | Each sub-search (people, products, places) returns a total field internally (e.g. people.total). However these are not summed or logged. A total result_count across all active sub-searches needs to be calculated and included in the event — zero-result searches are especially valuable as unmet demand signals. |  | Matches the number of results the search actually returned.
F55 | search_performed | server_ts | datetime | 2026-11-04T09:10:00Z | Useful | R7 | When | Backend system clock at the moment the action was handled. | Will add | No timestamp is stamped on the search response or logged anywhere. new Date().toISOString() at the point the search resolves is all that's needed — straightforward to add when the event emission is implemented. |  | UTC, ISO 8601, millisecond precision, and not equal to the time the event was ingested.
F56 | identity_stitched | anonymous_id | string | anon_c81f | Important | R6 | The pre-login identifier | The pre login device or session identifier. | Will add | No anonymous identifier exists anywhere — Flutter generates no guest ID before login, and the backend has no concept of a pre-login session. Flutter must generate a persistent UUID on first app launch, store it locally, and pass it to the login endpoint. The backend must accept and record it. |  | Matches the identifier used on the pre login events for that device.
F57 | identity_stitched | user_id | string | usr_4471 | Important | R6 | The account it was linked to | The authenticated user on the request context. | Will add | Available at login time from the authenticated user record. The POST /login endpoint (commonRouter.js:37) resolves the user and returns their ID — it just needs to emit the identity_stitched event pairing {anonymous_id, user_id} after successful authentication. |  | Populated on every event from a logged in session, and resolves to a user document.
F58 | identity_stitched | stitch_ts | datetime | 2026-11-04T09:14:00Z | Important | R6 | When the link was made. Recorded rather than applied silently, so history can be reconstructed | Backend clock at the moment the link was made. | Will add | No stitch event exists so no timestamp is recorded. Once the event is emitted at login time, stitch_ts: new Date().toISOString() should be stamped at the moment authentication succeeds — not at token issue or session creation, but at the point the anonymous_id → user_id link is confirmed and written. |  | Present on every stitch, and the stitch is recorded rather than applied silently.
F59 | order_placed | checkout_id | string | chk_2210 | Blocking | R4 | The identifier shared by every order created from one checkout. Q04 confirms a basket of five products becomes five separate orders, each with its own delivery, seller and fulfilment. Without a shared identifier those five are indistinguishable from five unrelated purchases, and what was bought together cannot be recovered. | Generated at checkout, before the orders are created, and written onto every order produced from it. | Will add | A checkoutModel exists (checkoutModel.js) and even has a virtual getter checkout_id returning this._id (checkoutModel.js:101). However it is entirely disconnected from the active order flow — createOrder (orderController.js:190) never creates a checkout document and the Order model has no checkout_id field. The checkout model is a legacy/unused schema. Currently every order is a single-product call (POST /order) with no shared basket identifier — a cart of 5 products produces 5 separate createOrder calls with no link between them. To implement checkout_id: a checkout session must be generated before the orders are created (at "place order" time in Flutter), written to the Order model as a checkout_id field on each order created from that session, and returned with every order_placed event. This is a new field on the Order model + a Flutter-side session ID generation — the existing checkoutModel is not the right vehicle for it as it is stale. |  | Place a basket of three products and confirm the three orders created carry the same checkout identifier and that no other order shares it.
Section 3. The eight data model changes. These are database changes rather than event logging, so they need a product decision and not only an engineering estimate.
ID | Item | Current position |  | What is needed |  | Priority | Where the change lands | Consequence if not done | Current status | Platform team notes |  | How to confirm it is done
D1 | Return capture on the order | Returns are handled offline. The buyer contacts the seller directly, the seller arranges collection, and money moves outside the app. Nothing is written to the order, which stays at its last status. Order Chat policy text and the Store Front policy field are not readable states. RETURN in stock history fires on cancellation as well as return, so it cannot distinguish the two and carries no order reference. |  | Two fields on the order model, and a Return control in order history that sets them. Refund, chargeback and any seller side workflow are out of scope by agreement. |  | Blocking | The order model, and the order history screen in the app. | A returned order is indistinguishable from a successful one, so the engine learns to promote items that sell and come back. Nothing else in the system carries that signal. | Will add | Returns are handled offline today and there is no appetite for a return workflow. This is the smallest version that still produces something usable, and it replaces the earlier ask for full return, refund and chargeback states. Two fields on the order model: return_requested: { type: Boolean, default: false }, return_requested_at: { type: Date, default: null }, Behaviour: the buyer taps Return in order history. return_requested is set to true and return_requested_at is set to the current server time. Nothing else changes. The order keeps its existing status. No seller workflow, no refund handling, no state machine. Both fields are required. The date is what distinguishes a purchase that has settled clean from one where a return may still be coming, so the boolean on its own leaves every recent order unusable. updatedAt cannot substitute, since it moves on every write to the order. Refund and chargeback are out of scope by agreement, not by omission. If a resolution state is added later, accepted or rejected, it would be used and nothing here changes shape. |  | Place an order, tap Return, and confirm both fields are written on the order document with a server timestamp.
D2 | One canonical order status (See Q06) | Confirmed by the platform response to F30: status is written across four parallel fields. The nine value claim in the platform ML schema reference is therefore a count across the four fields rather than one enum, and no single authoritative field has been nominated yet. Q06 stands. |  | Nominate one field as authoritative for outcome purposes, with the value set documented. |  | Blocking | Nomination rather than code. One of the four existing status fields is named authoritative. | No agreed definition of a successful order, so no consistent target for any model to optimise. | Already captured | order_status is authoritative and Delivered is the success signal. One action item remains, either drop seller_delivery_status or enforce a sync write. |  | The named field is written on every order and its value list is documented.
D3 | Shared checkout identifier across sibling orders (See Q04) | Answered in Q04. A basket of several products is checked out together but written as one order per product, because delivery, seller and fulfilment differ. The orders carry no shared identifier, so the basket cannot be reassembled afterwards. |  | A checkout identifier generated before the orders are created and written onto every order produced from that checkout. Line items on a single order are not required, and the split is a reasonable design given different sellers and delivery dates. |  | Blocking | The checkout flow, and a field on the order document. See F59. | Items bought together cannot be identified, so the co-purchase method for the product ranker cannot be built at all. The ranker falls back to attribute similarity alone and the second candidate method has nothing to compete against. | Will add | No checkout_id exists in the live system. createOrder creates one order per product — each order is fully independent with no shared basket identifier. The legacy checkoutModel has a virtual checkout_id getter but is completely disconnected from the active flow. The active orderModel has no checkout_id field. Status: Needs discussion — adding checkout_id requires both a new field on orderModel and a basket concept before createOrder is called; it cannot be retrofitted easily. |  | Place a basket of three products and confirm the three resulting orders share one checkout identifier.
D4 | Campaign entity (See Q02) | No campaign object exists. Promo codes are not campaigns. |  | A campaign entity that opportunities, promotions and commissions can reference. |  | Blocking | A new collection, with opportunities and promotions referencing it. | Campaign outcomes cannot be measured or attributed, and brand to promoter matching has nothing to learn from. | Needs discussion | Current status (confirmed): No campaign collection exists anywhere in the model layer. Only promoCodeRoutes exist — promo codes are flat discount records with no campaign parent. The opportunityModel does not exist either (no matches in /src/model). There is no object that opportunities, promotions, or commissions can reference as a campaign. Status: Needs discussion — requires a new Campaign collection + foreign-key wiring into promo, opportunity, and InfluencerEarning models. |  | A campaign can be created, listed and referenced by an opportunity.
D5 | Promoter and influencer as account states | Neither exists as an account state. Influencer appears only as an analytics screen. |  | Explicit account states, with transitions timestamped. |  | Important | The user document, as an effective dated state rather than a current value. | Promoter behaviour cannot be separated from ordinary user behaviour in the data. | Needs discussion | Current status (confirmed): Neither "promoter" nor "influencer" appears as a field on registerModel or businessRegisterModel. The user document has no accountRole, no isPromoter, no isInfluencer, no state transitions and no timestamps. isInfluencerPost exists on createPostModel (a flag on a post, not the user). The influencer analytics screen is a separate collection — it is not linked to an account state on the user. Status: Needs discussion — requires adding an effective-dated state field (e.g. accountRole: {type, since: Date}) to both user and business models. |  | A promoter's standing can be read as at a past date, not only as it is today.
D6 | Timestamped social interactions | Likely stored as counters on the item rather than as events. |  | Each interaction recorded as its own document with user, target, action and timestamp. |  | Important | Each interaction written as its own document rather than incrementing a counter. | Counters give a total but not who or when, which makes them useful as a feature and useless as a learning signal. | Partially captured | Current status (confirmed): Social interactions (follows, likes, shares) are stored as counters only: followerCount / followingCount — integer counters on registerModel likesCount / sharesCount / commentsCount — integer counters on createPostModel FollowModel does have timestamps: true so a follow relationship is individually dated — this one is partially captured Like (FavoriteModel) and bookmark (BookmarkModel) records exist per-user-per-post — also timestamped implicitly But shares, comments-count, and view counters are pure increments — no per-interaction document with user + target + action + timestamp Status: Partially captured — follow/like/bookmark have per-record documents (timestamped). Shares and comment actions are counters only with no attribution document. |  | Two likes on one post produce two rows with different timestamps and actors.
D7 | Stable identifiers | To be confirmed. |  | Entity identifiers are not reused when a record is deleted and recreated. |  | Important | Identifier generation across all entities. | User and item histories fragment silently, and no error appears anywhere. | Already captured | Current status (confirmed): MongoDB ObjectId values are never reused by design — once a document is deleted, its _id is gone permanently; a new document gets a fresh ObjectId. No custom ID generation, no sequential IDs, no ID recycling logic found anywhere in the codebase. This is safe by default. One gap: FollowModel and followerModel use userId / followingId as String (not ObjectId) — this means if a user document is deleted and recreated with the same string ID (impossible with ObjectId, but worth noting as a type inconsistency already flagged as D01). Status: Already captured — ObjectId generation is stable by MongoDB default. The D01 String-vs-ObjectId type defect is the related risk, not identifier reuse. |  | Delete and recreate a test record and confirm the identifier is not reused.
D8 | Raw event retention | To be confirmed. |  | Raw events retained twelve months minimum. Aggregates are not a substitute. |  | Important | Retention policy on the event store. | Training windows are truncated and seasonal patterns cannot be learned. | Needs discussion | Current status (confirmed): UserEvent is the primary ML training signal and it has a 90-day TTL (expireAfterSeconds: 7776000) — events older than 90 days are permanently auto-deleted by MongoDB. No export pipeline exists yet, so that data is gone with no recovery path. PostEvent (influencer analytics) has no TTL and is retained indefinitely, so it is safe. Orders and StockHistory are also retained indefinitely. Other collections — SecurityEvent (2 years), UserLoginHistory (365 days), UserSession (30 days) — have TTLs but are not ML training signals. The critical problem is UserEvent alone: 90 days is well short of the 12-month minimum the spec requires, and every day without an export pipeline means training data is being permanently lost. Status: Needs discussion — the UserEvent TTL must be extended or removed before an export pipeline is live. Once export is running, the TTL can be re-evaluated as a storage hygiene measure rather than a hard delete. |  | Retention is set to twelve months minimum and raw events are not aggregated away.
D9 | Incognito activity excluded from learning | isIncognitoMode exists on the order model. Events carry no equivalent flag, so incognito browsing cannot be separated from ordinary browsing. |  | An incognito flag on every event, and an exclusion rule removing incognito activity from user profiles and from training data. |  | Important | The event payload, and the eligibility rules applied before and after scoring. | Incognito activity is learned from and reflected back to the user, which is the opposite of what the mode promises. It is a privacy exposure as well as a modelling defect. | Partially captured | Current status (confirmed): isIncognitoMode: Boolean exists on orderModel and is correctly excluded in two places already: feedController.js:781 — isIncognitoMode: { $ne: true } when reading purchase history for co-purchase signals ProductController.js:91-93 — filters isIncognitoMode: false when building "friends who bought" social proof Gap: isIncognitoMode flag is only on orders — it does not exist on PostEvent, UserEvent, or TrackingModel. So incognito browsing (views, clicks, saves) generates analytics events with no flag to exclude them from ML training. Only the final purchase step is masked. Status: Partially captured — incognito is correctly excluded from order-based signals. All browse/engagement events (PostEvent, UserEvent) carry no incognito flag, so incognito browsing leaks into training data. |  | Place an order in incognito mode and confirm the events carry the flag and are excluded from the user profile.
Section 4. The exploration slice. Read this before responding to field F14.
What is being asked |  | For a small share of requests, in the region of three to five percent, return a list that is shuffled or that includes items the ranking rules would not have picked. Flag those requests with is_exploration so they can be identified later.
Why it looks wrong |  | It reads as deliberately showing some users worse recommendations, which is exactly the kind of thing that gets removed during a launch push.
Why it is necessary |  | The engine can only learn from outcomes it observes. If the app only ever shows what the launch rules already favour, no outcome is ever observed for anything else. Those items are never shown, never clicked, and therefore look uninteresting in the training data. The model inherits the launch rules' blind spots and cannot discover anything they missed.
Why it must be set at launch |  | Introducing randomisation into a live product later is a visible change that needs its own approval. Setting it at launch, when nobody has a baseline expectation yet, costs almost nothing.
What is negotiable |  | The percentage, which surfaces it applies to, and whether it runs continuously or in bursts. Whether it exists at all is not, because without it the learned models cannot improve on the launch rules.
Schema reference model | Capture register equivalent | Same thing? | Their priority | Register priority
RecommendationImpression | E2 recommendation_impression, E3 recommendation_click | Yes, with one difference below | F1, backlog | Blocking
ABExperiment | The variant and exploration fields, F14 and the policy stamp F06 | Overlapping, not identical | F2, backlog | Blocking
SearchLog | E11 search_performed | Yes. Theirs is richer | H4, sprint 1 | Useful
ContentFeedback | Negative feedback, not yet a register event | New. We agree it is needed | M2, sprint 2 to 3 | Not yet listed
SessionLog | F04 session_id on events | Different. Theirs is a session record, ours is a field | M1, sprint 2 to 3 | Important

## Questions to be answered on 4th
14 questions. Please write your answer in column F and set the status in column G.
No | Reference | Question | What we found on 3 September | Where to look | Your answer | Status | Task | What you actually do | Why it is needed, in plain language | Which model family needs it
1 | PT-08, D01 (High) | Is the posts.userId fix done in the database, or only planned? You marked PT-08 as Done. Your note explains the fix. We want to know if the migration was run. | We read 6 posts. userId is still a String in all 6. We took one userId and searched the users collection. Direct match: 0 rows. After we changed it to ObjectId: 1 row. So the join still returns nothing. | createPostModel.js line 105 All controllers that create a post | Not done in the database — only the schema is planned. The createPostModel still declares userId: { type: String, required: true }. No migration script exists in the codebase. The fix has been noted as a required change but no updateMany or migration has been run against existing documents. Every existing post in production still has userId stored as a plain string. The join failure risk (D01) remains live. | Done | Run the posts.userId migration | Change createPostModel to ObjectId and run an updateMany converting every existing post's userId from String to ObjectId. Confirm the join to users returns rows afterwards. | Confirmed in Q1: the fix was described but never run, and every post still holds a string. The join returns nothing rather than failing, so the loss is silent. | M1, M2, M4, M8. Every feature that connects a post to its author. The interest model cannot read who wrote what a user engaged with. Retrieval cannot find posts by an author the user follows. The promoter score cannot count a promoter's own posts, because it cannot tell which posts are theirs. | Post — userId → changed from String to ObjectId Order — user_id → was ObjectId with wrong ref, now correct refPath Checkout — user_id → same as Order All 3 models — added userModel field ('user' ¦ 'businessRegister') to identify User vs Business account Status: ✅ Done
2 | Capture register F59 (High) | Can the app send one checkout_id on all the orders from one basket? Our suggestion: the app makes the id one time when the user presses Pay. Then it sends the same id on every createOrder call. The backend only has to save it. | checkoutModel is not used anywhere. It is old code. Orders have no field that links them together. createOrder takes one product per call. So a basket of 5 products makes 5 calls. | orderController.js createOrder The checkout screen in Flutter | Yes, the suggestion works exactly as described. The Flutter side generates one UUID when the user taps Pay, then passes it as checkout_id in the body of every createOrder call for that basket. The backend only needs to: (1) add checkout_id: { type: String, default: null } to orderModel, (2) read it from req.body in createOrder and write it to the new Order. No basket logic, no server-side generation needed. This is the lowest-effort path to F59. | Done | Add checkout_id to the order | Add checkout_id: { type: String, default: null } to orderModel. Read from req.body in createOrder and write it. Flutter generates one UUID at Pay and sends it on every call for that basket. | Agreed in Q2. A five product basket becomes five unlinked orders, so what was bought together cannot be recovered. | M5, the product ranker. Its first method ranks by what people buy alongside the current item. Without this the method cannot be built at all, and M5 falls back to attribute similarity only, which is weaker and leaves nothing to compare against. | checkout_id added to Order checkout_id: String, default: null added to orderModel. Flutter generates one UUID per cart session and sends it with every order in that basket. All orders sharing the same checkout_id were bought together. Single/direct orders have null. Status: ✅ Done
3 | Capture register F34, F35, PT-11 (High) | Which field holds the payment state? And does the Razorpay webhook exist today? We have three different answers in three documents. We need one. | Orders have BOTH fields: payment_status = Pending on all 5 orders is_Payment = false on all 5 orders razorpay_payment_id is empty on all 5 orders. PT-04 says payment_status is set by hand by the seller. The Codebase Q&A of 3 September says payment_status does not exist and only is_Payment is used. | orderModel.js The Razorpay webhook file, if it exists | One authoritative answer: payment_status is a proper String enum on orderModel with values "Pending", "Completed", "Failed" (line 89–93 of orderModel.js). There is also a legacy boolean is_Payment on the same document — both exist and both get set together when payment completes (payment_status = "Completed" and is_Payment = true). Use payment_status as the ML field — it is the enum, not the boolean. Razorpay webhook: No webhook handler exists in the codebase. The Razorpay npm package is installed (v2.9.5) but there is no /razorpay/webhook or /payment/webhook route. Payment confirmation today is triggered manually — the app calls a confirmPayment endpoint which sets payment_status = "Completed" and is_Payment = true. There is no server-to-server Razorpay callback. | Not started | No change required |  | payment_status is the field to use, values Pending, Completed and Failed. is_Payment is legacy and must not be read. Note that Completed is set by the app calling confirmPayment, not by a gateway callback, so it records a client assertion rather than verified settlement. Column K: M9 fraud and risk. An app-asserted payment is a route to inflating a promoter's numbers without money moving, so it becomes a low confidence input to the fraud rules rather than a label.
4 | Capture register D1 (High) | What is the field return_type? Is it the seller policy, for example this product cannot be returned? Or is it a record that a return happened? Please send the full list of values it can hold. | All 5 orders have return_type = 'No Return'. It is the only return field on the order. | orderModel.js, the return_type field | return_type is a seller-set delivery policy field — it describes whether the product can be returned, not whether a return happened. It is a free-text String with default: "No Return". There is no enum constraint on it, meaning any string can be written. In practice the values used are whatever the seller enters — the codebase enforces no fixed list. It is set by the seller at order confirmation time (alongside deliveryTimeInDays), not by the buyer. It is not a return event record. A return happening has no dedicated field or model today (see Q5 below). | Not started | No change required |  | return_type is a free text seller policy field describing whether a product can be returned. It is not a return event and must not be read as one. It has no enum, so any string can be written. | None. Recorded so nobody mistakes it for the return signal added in Q5
5 | Capture register D1 (High) | Can you add these two fields to the order? return_requested: Boolean, default false return_requested_at: Date, default null When the buyer presses the Return button in order history, set return_requested to true and set the date to the server time. Nothing else changes. No seller screen, no refund, no workflow. Both fields are needed. Without the date we cannot tell an old order that was never returned from a new order that may still be returned. | There is no way to know a return happened. Returns are done on phone and courier, outside the app. | orderModel.js Order history screen in Flutter | Yes, straightforward to add. Neither field exists on orderModel today. The change is: In orderModel.js: return_requested: { type: Boolean, default: false }, return_requested_at: { type: Date, default: null }, In the order controller, whichever endpoint the buyer hits for "Request Return" — set return_requested = true and return_requested_at = new Date(). No other logic changes. This is a clean additive change that won't break anything existing. | Not started | Add the two return fields | Add return_requested and return_requested_at to orderModel, set when the buyer requests a return in order history. | Agreed in Q5. Returns happen offline and leave no trace, so a returned order looks identical to a successful one. | M4, M5, M8. All three carry a commerce term. Without a return signal they learn that an item which sells well is good, including items people buy and send back. M8 is worst affected: a promoter driving returned sales scores the same as one driving kept sales.
6 | Capture register F24 (High) | Why is post_id not saved on the order? The cart saves it. The Codebase Q&A says createOrder accepts it. But no order has it. | carts.post_id: 1 of 1 cart has it. orders.post_id: 0 of 5 orders have it. This is the link that tells us which post caused a sale. Without it we cannot pay credit to the right promoter. | orderController.js createOrder The checkout call in Flutter | post_id is accepted in createOrder's req.body and used immediately for influencer analytics (firing a PostEvent with event_type: "purchase"), but it is never written into the Order document itself. The new Order({...}) block on line 306 of orderController.js does not include post_id. The orderModel has no post_id field. So the cart passes it, the controller reads it, the analytics use it — then it is discarded. To fix: add post_id: { type: mongoose.Schema.Types.ObjectId, ref: "Post", default: null } to orderModel and include it in the new Order({...}) constructor. | Done | Persist post_id on the order | Add post_id to orderModel and include it in the new Order({...}) constructor at orderController.js line 306. | Confirmed in Q6. It is accepted in the body and used to fire the purchase PostEvent, then discarded. | M8 and M6. This is the link that says which post caused a sale. Without it a promoter's commercial impact cannot be measured from orders, and M6 cannot estimate what a promoter would earn from an opportunity. It also feeds the commerce term in M4, since it tells the feed which content actually converts. | post_id was already read from req.body but never saved — now persisted. Added post_id: ObjectId, ref:"Post", default:null to orderModel + written in new Order({...}). When a user buys from a feed post, Flutter sends the post_id — it's now stored on the order. Direct orders have null. Status: ✅ Done
7 | Capture register F04 (Medium) | What creates session_id on post events? We think it is one id per view, not one id per session. Please confirm. If we are right, is there any id that stays the same while the user is using the app? | 13 view events have session_id. All 13 values are different. One user has 5 events and 5 different ids. The values look like: fv_6a5a3b52...._1784299794505 Only view events have it. Like, save and purchase events do not. | postEngagementController.js, trackPostView | One per view, not one per session. Confirmed in Flutter: _sessionId = 'fv_${widget.postId}_${DateTime.now().millisecondsSinceEpoch}'; A new _sessionId is generated each time a post becomes visible for ≥ 3 seconds. The format is fv_<postId>_<timestamp> — it encodes post + moment, not user + app session. Two views of the same post in the same app session get different session_id values. There is no app-session-level ID that stays constant while the user is using the app. The closest thing is the user's auth token, but that is not passed as an event field. If ML needs a stable app-session identifier (one ID from app open to app close), it needs to be generated at login/app-launch in Flutter and passed on every event. | Not started | No change required in Sprint 1 |  | There is no app session identifier. session_id on post events is one value per view. F04 moves to Deferred and session scoped features come out of the launch feature list. Separately, the three second visibility rule already implemented becomes the qualified view definition. | M1. Session features are dropped. The three second threshold is adopted for the label work rather than a new one being invented.
8 | Capture register D8, Q10 (Medium) | The 90 day auto delete on userevents is not active in the database. Please check. Important: Mongoose does not change an index that already exists. The index timestamp_1 is already there without the delete rule. So adding expireAfterSeconds in the schema will not work. Someone must drop the index and create it again. | userevents has 0 documents. Indexes present: _id_, timestamp_1, userId_1 None of them has expireAfterSeconds. The schema file says 90 days. | userEventModel.js line 23 Run db.userevents.getIndexes() | The ML team is correct. Mongoose does not modify an existing index — if timestamp_1 was created before expireAfterSeconds was added to the schema, MongoDB keeps the old index as-is and silently ignores the new schema definition. The TTL is only in the schema code; it has never been applied to the running index. To fix it, someone must run these two commands directly in MongoDB (not in code): db.userevents.dropIndex("timestamp_1") db.userevents.createIndex({ timestamp: 1 }, { expireAfterSeconds: 7776000 }) Until that is done, UserEvent documents are never deleted — the collection grows forever. Once the ML export pipeline is live, the index should either be dropped entirely (no TTL) or extended well beyond 12 months. | Not started | Rebuild the userevents index | Drop timestamp_1 and recreate it with the intended retention, or leave it without expiry until the export exists. Run in MongoDB directly. | Confirmed in Q8. Mongoose does not modify an existing index, so the 90 day rule in the schema has never applied. | M1, and every Wave 1B model. The interest model reads user events. Nothing is being deleted today, which is currently in our favour, but the retention has to be decided deliberately rather than left in a state nobody intended.
9 | PT-12, capture register (High) | The interest categories do not match each other. Please tell us which list is correct. There seem to be three different lists in the system. We need one list before we build the interest score. | The categories collection has 8 names: Casual Sneakers, Fashion, Fashion Accessories, Footwear, Jackets, Men's Clothing, Saree, Sunglasses. But users.interestScores uses these names: Electronics, Fashion, Home & Living, fashion, fashion & apparel, shoes & footwear. Four of them are not in the categories collection. Fashion and fashion are both used. They are counted as two different things. | The onboarding interest screen Whatever code writes users.interestScores categories collection | Three lists confirmed in the codebase: List 1 — Interest selection at signup (interest_selection_screen.dart, 28 items): Fashion, Beauty & Skincare, Electronics, Jewellery, Shoes, Bags & Wallets, Watches, Kids & Baby, Home & Decor, Kitchen & Dining, Garden & Plants, Bedding & Bath, Health & Wellness, Fitness & Gym, Sports, Food & Beverages, Organic & Eco, Technology, Automotive, Photography, Travel, Wedding & Events, Education, Finance, Art & Handmade, Music, Pets, Gaming List 2 — Post category picker (category_picker_screen.dart, 23 items): Fashion & Apparel, Electronics, Food & Beverages, Home & Living, Beauty & Personal Care, Sports & Outdoors, Automotive, Travel & Lifestyle, Health & Wellness, Books & Education, Pets, Art & Collectibles, Toys & Kids, Music & Entertainment, Office & Business, Technology, Jewellery, Shoes & Footwear, Organic & Eco, Photography, Finance, Gaming, Wedding & Events List 3 — Product categories — fetched dynamically from MongoDB categories collection via /api/categories. No fixed enum — sellers create them. These lists do not match. The interest scoring in feedController.js cross-matches post.categories (from List 2/3) against user.interestScores (built from List 1 keys). Because the label names differ (e.g. "Fashion" vs "Fashion & Apparel", "Sports" vs "Sports & Outdoors"), most cross-matches silently produce zero score. The platform team needs to decide on one canonical list. The recommendation is: use the post category picker list (List 2) as the master, align signup interests to match those exact labels, and ignore the free-form product category collection for scoring purposes. | Not started | Align the interest and category lists | After the decision, adopt one canonical list, change both screens, and migrate existing interestScores keys. | Confirmed in Q9. Three lists exist with different labels, so most interest matching scores zero today. | M1 and M2, and through them everything else. The interest model is held per category, so mismatched labels split one interest across several and match nothing. Retrieval matches a user's interests to a post's category, which fails for the same reason. Both are the first models built and every later model reads their output. It also breaks the delivered interest score, which is the fallback the whole system degrades to. | Status: Done Task: Align the interest and category lists What was done: Adopted one canonical list of 23 categories as the single source of truth. Created src/constants/categories.js (backend) and lib/core/constants/app_categories.dart (Flutter). Replaced the old 28-item onboarding short-label list with the exact 23 canonical labels. Fixed key normalization in trackEvent and trackInteraction in feedController and adminService — was storing "fashion_&_apparel" (underscores), now stores "fashion & apparel" (spaces, lowercase) matching the feed scorer. Fixed addInterest to normalize keys the same way. Wrote a one-time migration script scripts/migrate-interest-scores.js to remap all existing users' interestScores keys from old formats to canonical. Confirmed in: Q9. Three lists existed with different labels, so most interest matching scores were zero. trackEvent stored underscore keys, addInterest stored raw short labels, feed scorer read space-separated lowercase — none matched. Migration script covers all known legacy formats including old onboarding labels, underscore keys, and seed script values. Impact: M1 and M2, and through them everything else. Interest score is now written and read with the same key format across all paths — onboarding, engagement tracking, and feed ranking. Retrieval matching between a user's interests and a post's category now works correctly. Delivered interest score (the fallback the whole system degrades to) is restored.
10 | PT-13 (High) | If user A blocks user B, how do we stop B's posts reaching A? Blocking today deletes the follow rows. That works for the feed, because the feed reads follows. Our engine also finds posts by matching the content, not by follows. That way does not look at follows at all. So a blocked user's post can still come through. Is there any other check that stops it? If not, we need a way to read the block list. | followers collection has 0 rows in the test database, so we could not check the block records. | followService.js blockUser feedController.js | Yes, it can. Here is the exact gap: The follow-based feed (feedType: "following") is safe — it reads FollowModel, and blocking deletes both follow records, so blocked users are excluded. The "for you" / trending / content-matched feed reads createPostModel directly and scores posts by category/interest matching — it does not check FollowModel or the block list at all. There is no query filter like userId: { $nin: blockedUserIds } anywhere in feedController.js. No other check exists that stops it. The ML engine will need access to the block list and must apply author_id NOT IN blocked_list before ranking. The block records are in followerModel where status: "blocked" and isBlocked: true — that collection is readable. Alternatively, the feed API can pre-filter post candidates by excluding blocked authors before passing candidates to the engine. | Not started | Exclude blocked authors from the for you feed | Add a filter excluding authors the viewer has blocked, before scoring. Block records are on followerModel with status: "blocked". | Confirmed in Q10. The following feed is safe because blocking deletes the follow edges. The for you feed reads posts directly and never checks. | M2 and the eligibility layer. Not a model input but a rule applied around every model. Content retrieval finds posts by similarity and never touches the follow graph, so a blocked person's post can reach a user through it. This is a live defect in the app today, independent of the engine.
11 | PT-13 (Low) | Is Mute really not built? The field isMuted is in the followerModel schema. The Codebase Q&A says mute is not built anywhere. If it is not built, we will remove it from our design. We only need a yes or no. | We could not check. followers collection has 0 rows. | followerModel.js followService.js | Partially — the field exists but no endpoint or service logic uses it. isMuted: { type: Boolean, default: false } exists on followerModel and is already read in one place: followService.getDynamicFollowers filters isMuted: false when building the follower list for feed. But there is no endpoint to set it — no /follow/mute route, no toggleMute function in followController or followService, no Flutter call that writes isMuted: true. The field is always false for every record. Short answer: the field is there, but mute is not usable today. Users cannot mute anyone because there is no endpoint to set the flag. Remove it from the ML design — it produces no signal. | Not started | No change required | Field exists and is read in the follower query, but nothing writes it, so it is false on every row. Removed from the feature and eligibility design. Adopt as a negative signal if mute is ever built. |  | M2 and the eligibility layer. Carries no signal today.
12 | Capture register section 3 (Medium) | Please set the status for the 9 rows D1 to D9 in the capture register. You have answered all 59 field rows. | Rows 85 to 93 in the Capture register tab are empty in the status column. | Capture register tab, column J, rows 85 to 93 |  | Not started | Done
13 | PT-07 (High) | How many milliseconds can the recommendation call take? Please give one number for the feed screen. For example 200 ms. We need it before we design. If we design first and the number comes later, we may build something too slow. | Not answered yet. PT-07 is still open. | The feed API today. How long does /dashboard-feed take now? | No SLA or timeout is defined in the current codebase. Based on the current feed implementation: The getDashboardFeed endpoint runs sequential MongoDB queries (tracking lookup → user fetch → follow list → post query → scoring). In production on a warm DB it typically takes 300–600ms end-to-end for the full feed page. There is no timeout enforced today. Recommended ML budget: 200ms. The feed must respond in under 1 second total; the app has no loading skeleton for the feed — it shows blank until data arrives. Allocating 200ms for the ranking call leaves 400ms for DB fetch + serialization + network. If the engine cannot guarantee 200ms at p95, add a 200ms timeout with fallback to the existing score-based ranking. | Not started | Confirm the budget by measurement | Allen measures the current feed call in RE-00e and confirms whether 200ms holds once the integration shape is known. State the budget at p95 and split it by stage. | The 300 to 600ms quoted is an average for the current feed including the scoring it already does. Whether the recommendation call adds to that or replaces part of it depends on how it is wired, so 200ms is provisional until measured. | M2 and M4. The budget bounds how large a model can be and whether scores are read or computed at request time.
14 | Q08 (Medium) | Where can we write the scores the engine calculates? We need a separate database or a separate collection prefix. The read-only user cannot write. We must not write into the app collections. | The credential you gave is read only, which is correct. | MongoDB Atlas, nex-dev cluster | The app uses a single MongoDB connection (MONGO_URL in .env) — one database, one connection. There is no second database, no ML-specific connection, and no collection prefix convention today. Two clean options for the ML engine to write scores without touching app collections: Option A — Prefix convention in the same database: All ML-written collections use an ml_ prefix: ml_user_scores, ml_post_scores, ml_recommendation_cache. The app's MongoDB user gets read-only on ml_* collections; the ML service gets its own write-capable credential scoped to ml_* only. No new infrastructure. Option B — Separate database on the same cluster: Create a second database (e.g. soco_ml) on the same Atlas cluster. The app reads from it with a separate connection string. The ML service writes exclusively there. Cleaner isolation, slightly more setup. Recommendation: Option A first. It requires no infrastructure change — just a new MongoDB user with collection-level permissions and the prefix convention agreed upfront. Move to Option B if the ML write load causes contention on the shared cluster. | Not started | Create the ml_ namespace and credential | Agree the ml_ prefix as a rule, create a write scoped credential limited to ml_*, and confirm the app's user stays read only there. | Option A accepted. The isolation only holds if the credential is genuinely scoped, so that is the condition rather than a detail. | All families. Every computed score is written here.

## Wave map
Wave map ¦ The nine model families across Wave 1A, Wave 1B, Wave 2 and Wave 3
Wave 1 is not a single stage. It splits in two. Wave 1A is what ships on launch day and works without any training labels, because it runs on scores, rules and similarity rather than on anything learned from user behaviour. Wave 1B is the supervised half, built after launch once real traffic has accumulated enough examples to train on.
Wave 2 and Wave 3 come later and are gated on measured data rather than on dates. Their columns here are indicative and nothing in them is committed.
A blank cell means nothing new happens for that family in that wave. It does not mean the family stops working. Once a family is live it stays live, and later waves replace the method inside it rather than switching it off.
Ref | Model family | Wave 1A, launch day | Wave 1B, post-launch | Wave 2 | Wave 3
M1 | Interest and profile | TWO METHODS. Recency decay serving, time windows challenging |  | Sequence or embedding profile
M2 | Content retrieval | ONE METHOD. Interests, follows, category and vector similarity |  | Two tower retrieval with an approximate nearest neighbour index | Principled exploration policy replacing fixed quota
M3 | First stage ranker | NOT LIVE. M2's shortlist passes straight through | TRAINED. Gradient boosted trees or logistic regression, chosen at training time against real volume |  | Distilled from the heavy ranker
M4 | Feed ranker | NOT LIVE. Feed order comes from the interest score and the heuristic ordering | TRAINED. Multi task network predicting several outcomes | Full positive and negative head set with calibration | Mixture of experts and sequence models
M5 | Product ranker | TWO METHODS. Attribute similarity serving, bought together challenging | Learned ranker over impressions and purchases | Two stage product recommender
M6 | Opportunity model | ONE METHOD. Expected value formula | Learned model over accepted and completed offers | Two tower retrieval with an outcome ranker
M7 | Brand match | NOT LIVE. Blocked on Q02, not on data | BLOCKED. Rules over the promoter score, available only once a campaign entity exists | Expected value ranker over completed campaigns
M8 | Promoter score | TWO METHODS. Shrinkage score serving, percentile cohort challenging |  | Learned calibration | Stable policy dimensions
M9 | Fraud and risk | ONE METHOD. Fixed thresholds | Outlier detection tuned on the observed distribution, compared offline rather than by traffic split |  | Graph models detecting coordinated behaviour
Reconciling the counts
The proposal describes nine model families across three engines. What ships on launch day is six families across two engines. Both statements are true and the bridge between them is below.
Statement | Count | Which
Model families specified in Wave 1 | 9 | All nine. Specification is methodology and does not depend on data
Model families built in Wave 1 | 8 | All except M7
Families running on launch day, Wave 1A | 6 | M1, M2, M5, M6, M8, M9
Methods running on launch day | 9 | Six families, three of which carry two methods each. This number matching nine families is a coincidence
Families added after launch, Wave 1B | 2 | M3 and M4. Trained work with people on it, not something that switches itself on
Families not built in Wave 1 | 1 | M7, blocked on the Q02 decision rather than on data
What this means for the three engines
Engine | Question it answers | Families serving it | Status on launch day
A. User to promotion feed | What should this person see? | M1, M2, M3, M4, M5, plus M8 and M9 shared | Working. M3 and M4 arrive in Wave 1B, so ordering comes from rules and the interest score until then
B. Promoter to opportunities | What is worth this promoter's effort? | M6, plus M8 and M9 shared | Working
C. Campaign to promoters | Who should this brand approach? | M7, plus M8 and M9 shared | Not working. M7 is its only dedicated family and it is blocked on Q02. A promoter score and a fraud filter alone do not rank promoters for a campaign
Three engines are specified. Two work on launch day. The third depends entirely on the Q02 decision.

## Model options
Design position ¦ Three models run two candidate methods from launch. The other six run one.
What is changing. Three model families carry two candidate methods rather than one: interest, product ranking and promoter score. Both are built. One serves the majority of traffic, the other serves a minority slice, and whichever performs better takes over once there is enough evidence to separate them.
Why only three. Choosing between two methods needs enough observations per method to tell them apart. On a new app that volume is not guaranteed for months, so running nine comparisons at once would mean paying for eighteen methods and still choosing most of them by judgement. These three were selected because their comparison does not depend on high traffic: all three can be judged against what users did next on a period held back from the calculation, rather than needing a live split to resolve.
What happens to the other six. They run one method at launch. The second candidate is recorded as a written position rather than as launch scope, and is revisited at the point where the data situation is visible rather than assumed. For the families that are not live at launch at all, that revisit happens naturally when the mature form is scoped.
The larger source of adaptability. Most of the gain from adapting to data comes from retuning the values inside a method rather than swapping the method: the decay rate in interest, the component weights and shrinkage strength in promoter score, the source quotas in retrieval, the thresholds in fraud. Retuning those needs the same configuration mechanism as the variant split, which is why PT-10 asks for configuration rather than code.
What this needs from the platform team. Only PT-10, and only for the three slots below. Two methods live at once with a configurable split, the split and default held as configuration rather than compiled constants, and assignment by a hash of the user identifier so a user does not alternate between methods. Everything else is data science work.
Governance. One family changes at a time. A challenger must beat the serving method by a stated margin on a stated metric, over a minimum number of observations, before it takes over. The switch is a human decision, not an automatic one, and it is reversible by changing a configuration value.
Ref | Model family | What it does, in plain language | At launch | Method serving from day one | Second candidate method | How and when the choice is made | Platform work
M1 | Interest and profile | Works out what each user cares about, from what they declared at signup and what they have done since. | Two methods live | Recency decay. Every action counts toward a category score, and older actions count for less on a smooth curve. Default because it extends the scoring engine the platform already runs, so a problem degrades to something familiar. | Time windows. Separate counts for the last 7, 30 and 90 days, combined with fixed weights per window. | Which one better predicts the category a user engages with in a later period held back from the calculation. Does not require a live traffic split to resolve, so a first read is possible within weeks of launch. | PT-10
M5 | Product ranker | Orders products on product and cart screens. | Two methods live | Similar products. Ranks by attribute similarity plus the seller's own cross sell list. Default only because the alternative needs order history that does not exist yet. | Bought together. Ranks by what has been purchased or carted alongside the current item. | How often the product the user later bought appeared near the top. This is the one expected to flip: as order volume grows, bought together should overtake attribute similarity, and having it already built is the point. | PT-10
M8 | Promoter score | Scores promoters on reach, quality, commercial impact and trust. | Two methods live | Weighted score pulled toward the category average when there is little evidence, so new promoters are not judged on two data points. | Percentile rank within a cohort of similar category and account size, so promoters are compared against their peers rather than against everyone. | Whether the ranking is stable month to month, and how well it lines up with the sales promoters actually generate. Computed from stored data, so no traffic split is needed. | PT-10
M2 | Content retrieval | Assembles the shortlist of posts and products a user might want, before anything is ranked. | One method | Interests and follows. Candidates drawn from declared interests, followed authors and the same categories. | Content similarity, recorded as a position. Needs engagement history before it can compute anything, so comparing it at launch would compare a working method against an empty one. | Revisited when retrieval is scoped for the next wave, at which point the comparison is against the mature two tower form rather than against a heuristic. | None
M3 | First stage ranker | Cuts a long shortlist down to a short one, quickly and cheaply. | Not live at launch | Nothing. The launch rules produce the ordering until there are labels to train on. | Gradient boosted trees and logistic regression are both recorded as candidates. Which is better depends on how much data has accumulated, which cannot be known in advance. | Decided when the model is first trained, against real volume. Choosing now would be guessing at a data situation that is not yet visible. | None
M4 | Feed ranker | Decides the final order of the feed. | Not live at launch | Nothing. The launch rules produce the ordering until there are labels to train on. | A single model predicting several outcomes at once, and separate single outcome models blended together, are both recorded as candidates. | Decided when the model is first trained. The choice turns on how many outcomes have enough examples, which is a measurement rather than a preference. | None
M6 | Opportunity model | Ranks products and campaigns by how worthwhile they are for a promoter to promote. | One method | Expected value formula. Commission rate multiplied by an estimate of how likely something is to sell and how many people it reaches. | A learned model over which offers promoters actually accepted and completed. Recorded as the successor rather than as a parallel option. | Takes over once there is a history of accepted offers, rather than competing against the formula from day one. | None. Depends on Q05
M7 | Brand match | Ranks promoters for a brand campaign. | Not live at launch | Nothing. Blocked until Q02 settles whether a campaign entity exists. | Rules over the promoter score, and affinity matching between campaign brief and promoter history, are both recorded as candidates. | Decided when the campaign entity exists and completed campaigns have accumulated. | None. Depends on Q02
M9 | Fraud and risk | Flags fake engagement, self purchase and referral abuse. | One method | Fixed thresholds. For example more than a set number of actions per minute. | Outlier detection with thresholds derived from the observed distribution. Deliberately not run as a live split, because a split here means one slice of users gets the weaker fraud filter, which is an exposure rather than a quality trade-off. | Compared offline against manually reviewed cases, at a fixed review budget. No traffic split at any point. | None

## Exit criteria
Sprint 1 ¦ Definition of done
Sprint 1 is complete when all the 3 criteria below are met. Neither can be met by the data science workstream alone.
# | Exit criterion | Satisfied by | Verified how | Status
1 | Launch feature list circulated for engineering confirmation | CL-02, CL-03, CL-04 on the Cristo Labs side. PT-06 on the platform side. | Every row on the feature list carries a verdict from engineering. No blanks. | Not started
2 | Metric set and acceptance thresholds agreed | CL-05, CL-06 on the Cristo Labs side. PT-04 on the platform side. | A written metric per model family, a named baseline for each, and thresholds separated into those checkable now and those that can only be set on live traffic. | Not started
3 | Engine environment ready and the candidate method position recorded | RE-00a to RE-00f, PT-10, and CL-08 to CL-11. | Both methods are specified for the three families running two at launch, the second candidate is recorded for the remaining six, the selection rule is written and the tunable parameters are published. The comparison itself cannot begin until live traffic exists. | Not started
Two things that will move the sprint if they slip
The read-only credential is dated day 1. Every day it slips moves the sprint by the same amount, because nothing else can start without it.
The canonical order outcome field, Q06 and PT-04, gates exit criterion 2 entirely. There is no way to agree a threshold for a target that has not been defined.