## Read me
M1 demonstration ¦ who does what, and what survives afterwards
Reference | SOCO-REC-DS-015
Version | 3.0. Supersedes v2. Fifteen changes, listed on the Changes tab.
Covers | The four working days to the M1 demonstration. Companion to SOCO-REC-DS-014 v2, which is the demonstration plan itself.
Owners | Allen owns the engine code. Kala owns the demonstration scaffolding: the generator, the data checks, the display script and the narration. Two short schema agreements sit between them and are marked as joint.
Related | SOCO-REC-DS-008 v3.1 the method specification, SOCO-REC-DS-012 v2 the build brief, SOCO-REC-DS-007 v1.1 the parameters, SOCO-REC-DS-014 v2 the demonstration plan, SOCO-REC-DS-018 the change register.
The three tags
• Actual build. Real engine code. It ships, it is what Sprint 2 delivers, and the demonstration happens to exercise it.
• Build, exercised by the demo. Real engine code that the demonstration puts under load in a way normal development would not. Same status as the above, listed separately so it is clear why it is being done in this window.
• For demo only. Scaffolding. Constructed data and a viewer. Neither is engine code and neither ships, though both stay useful afterwards for regression checks.
The rule that makes this work
• There is no demo branch and no demo_decay.py. The demonstration runs the real engine code against constructed events.
• Two configuration values make that possible: the collection the methods read from, and the collection they write to. The demo run points at ml_demo_events and ml_user_interest_scores_demo. The real run points at postevents and ml_user_interest_scores. Nothing else differs.
• If something has to be special cased to make the demonstration work, that is a finding about the build rather than a shortcut to take. Raise it.
• The split of work follows the tags. Allen builds engine code only. Kala builds the generator, runs the data checks, writes the display script and prepares the narration. This takes roughly a day off Allen and removes the crunch on day 1.
• Two dependencies run between them and both are short. The event row schema must be agreed on day 1 before the generator is written, and the score row field names on day 2 before the display script is. Neither takes more than half an hour and both are marked as joint tasks.
On task numbers
• Renumbered in version 3, because a task was added before the four days begin and nothing outside this sheet refers to a task by number. Twenty two tasks rather than twenty one.
• User identifiers are the opposite case and were deliberately not renumbered when the dataset changed, because DS-014 and the running order refer to them.

## Changes
Changes in version 3 ¦ from checking this sheet against DS-008 v3.1, DS-007 v1.1 and DS-014 v2
Ref | Where | Was | Is now | Why it matters
C-47 | Purchase reversal task | Applies the same weight negatively at the cancellation timestamp. | Applies the same weight negatively aged from the original order's creation timestamp. | This is the sheet Allen works from day to day. It told him to build the thing DS-008 v3 corrects: aged from the cancellation the reversal removes more than the purchase added and can drive a raw score negative.
C-48 | Event row schema, and the generator task | Five fields: user_id, event_type, category, timestamp, weight. | Seven: categories as an array, plus view_duration_seconds on view events and order_id on purchase and reversal rows. | U02 needs a duration, U03 needs multiple categories, U16 and U17 need the order identifier so the reversal can be aged from it.
C-49 | Generator task | Twenty users. Categories from the canonical twenty three only. | Twenty narrated users plus 150 to 200 filler users prefixed F. Canonical except U06, U08 and U10. Declared interests on the user record, never as events. Four values pinned that the plan left open. | Three of the new users exist to demonstrate mapping and dropping, which the old rule forbade the generator from producing. The four pinned values decide whether their steps work: at a thirty day half life, two of the plausible defaults invert the result they are meant to show.
C-50 | Data checks task | Four checks. U04 to U06 have sixty days between old and new activity. U07, U08 and U11 emit no events at all. | Seven checks, matching DS-014 v2 section 3.3. | Both of those checks were false against the current dataset. U05 and U06 demonstrate something else now, and U08 carries fifteen product events, six of them deliberately unmappable.
C-51 | Narration task, first dry run | Eight demonstration steps. | Ten. | DS-014 v2 added steps for the purchase reversal and for what the model refuses to count.
C-52 | Second dry run | Fifteen minutes. If it runs long, drop steps 3, 6 and 7. Never step 8. | Seventeen minutes against a fifteen minute slot. Drop 9, then 8, then 3. Protect 10. | The step numbers referred to the old running order, so the instruction pointed at the wrong steps in both directions.
C-53 | Anticipated questions | Three. | Four. The new one is why the dataset is only twenty users. | The project team has already raised it.
C-54 | Conformance task | With decay disabled, method one reproduces the delivered score exactly on a replayed event set. | Same, on the restricted replay set defined in DS-008 v3.1 section 6.1, and dependent on D-01. | Four rules in the specification have no counterpart in the delivered engine. A replay set containing them fails by construction and reads as a defect in Allen's code. If the delivered function cannot be called standalone, the test compares against a reimplementation and asserts nothing.
C-55 | Cold start task | U07 has declared interests only, U11 has nothing. | Same, with the rungs named, and rungs 4 and 5 falling through to rung 3 with the fall-through logged. | The delivered score that rungs 4 and 5 fall back to exists for two of twelve users.
C-56 | Method one task | Declared interest contributes a non decaying floor. | Same, held as P-25 with P-26 governing whether it decays, both read from configuration. | The floor was folded inside P-06 until DS-007 v1.1. It is its own configuration value now and Allen builds the layer against the list.
C-57 | New task | No task covered the open questions to Aravinth. | Task 4. D-01, D-02 and D-03, needed by day 1. | Two of them gate the conformance test, which is a day 4 task, and they sat in the register with a day 1 need date while appearing nowhere on the sheet that drives the four days.
C-58 | Read me, Related | DS-008 v2, DS-012, DS-007, with no versions on two of the three. | Current versions of all five related documents. | Two versions of DS-008 and DS-012 now exist. A reference without a version resolves to whichever copy is nearest.
C-59 | Not in these four days | The full fallback ladder, RE-05. Only the cold start rungs are shown. | Rungs 4 and 5 only. Rungs 2 and 3 are in scope and are demonstrated. | U07 is rung 2 and U11 is rung 3. They are different code paths, and the sheet excluded work it also required.
C-60 | Footer count | 13 of 21 tasks are real engine code and all of them are Allen's. | Fourteen of twenty two, of which ten are Allen's alone, two joint and two Kala's. | Three tasks tagged Actual build are Kala's or joint, so the count and the claim contradicted each other.
C-46 | Task numbering, and the status of tasks 1 and 2 | Twenty one tasks, both of the first two Not started. | Twenty two, renumbered. Task 1 complete, task 2 part complete. | Task 1 is what produced this round of changes. Nothing outside this sheet refers to a task by number, so renumbering is safe here in a way it was not for the user identifiers.

## Task list
Four days to the demonstration ¦ every task tagged by whether it ships
# | Day | Owner | Task | What done looks like | Tag | Sprint 2 ref | Status
1 | Before | Kala | Confirm the twenty user definitions against the method specification | Complete, 9 September. Every user traces to a behaviour DS-008 describes and the trace sits in section 3.2 of DS-014 v2 as a column. Eight users proved nothing their twin did not and their slots now carry eight behaviours the specification defined and no user exercised. Four specified behaviours remain uncovered and are recorded as decisions rather than gaps. | For demo only |  | Complete
2 | Before | Kala | Confirm the parameters in SOCO-REC-DS-007 v1.1 | Part complete. P-04, the thirty day half life, is read and accepted, and the dataset is verified against it. P-03 attribution window and P-15 shrinkage strength are still to be read. Version 1.1 adds P-25, P-26 and P-27, corrects P-06 and rescopes P-07, so Allen builds the configuration layer against twenty seven parameters rather than twenty four. | Actual build | CL-11 | Part complete
3 | Before | Allen | Confirm whether anything writes to UserEvent | A repository search for userEventModel establishing whether any controller calls create or save on it. Five minutes, and it decides whether four features need respecifying. | Actual build | PT-19 | Not started
4 | Before | Kala | Put the three open questions to Aravinth | D-01, can the delivered scoring function be invoked on a constructed event set outside the app. D-02, is its product view increment gated on a duration threshold. D-03, does it credit each category of a multi-category post fully. D-01 and D-02 are needed by day 1 because task 19 depends on them. A fourth is worth adding: at what point does the delivered engine credit the purchase weight, order placed or Delivered. | Actual build | RE-08 | Not started
Day 1
5 | 1 | Allen | Score store with the four metadata fields | ml_user_interest_scores holds one document per user per category carrying raw, share, event_count, method, version, window and computed_at. Write scoped credential limited to the ml_ prefix. The app credential stays read only there. | Actual build | RE-02 | Not started
6 | 1 | Allen | Make the source and target collections configuration | Neither method contains a hardcoded collection name. A config value selects ml_demo_events or postevents for reading, and the demo or live score collection for writing. This is what removes the need for a demo branch. | Actual build | RE-02 | Not started
7 | 1 | Kala and Allen | Agree the event row schema, thirty minutes | Seven fields fixed in writing before anything is built: user_id, event_type, categories as an array, timestamp, weight, view_duration_seconds on view events, order_id on purchase and reversal rows. Field names agreed exactly, so the generator and the methods do not diverge. Declared interests are not events and do not appear in this schema at all. | Actual build | RE-02 | Not started
8 | 1 | Kala | Event generator script | A checked-in script with a fixed random seed producing twenty narrated users into ml_demo_events, plus 150 to 200 filler users prefixed F for platform wide popularity. Seven fields per row. Canonical categories except U06, U08 and U10, which carry mappable, unmappable and malformed values deliberately. Declared interests written on the user record. Events spread over 120 days. U16 and U17 carry the purchase reversal rows with the order identifier. Four values pinned: U05's twenty five events are all product views at weight 2, U04's Electronics carries at least 1.2 times the raw weight of Home & Living, U18's ninety one day event sits in its own category, and U12 and U13 hold the same age distribution across both their categories. | For demo only |  | Not started
9 | 1 | Kala | Run the seven data checks | The seven checks in DS-014 v2 section 3.3, run on day 1 rather than day 2 because Allen's decay sanity check on day 2 depends on the data being right. Check 7, that U16 and U17 differ by exactly the purchase contribution with no negative raw, is the one that catches the reversal if it has been built the old way. | For demo only |  | Not started
Day 2
10 | 2 | Allen | Method one, recency decay | Computes and writes a score per user per category. Half life P-04 and event weights P-06 read from configuration, never hardcoded. The declared interest contributes the floor held as P-25, which does not decay while P-26 is No, and is read from the user record rather than from the event stream. Share computed and stored alongside raw. Category held as a map key with no hardcoded list anywhere. | Actual build | RE-03 | Not started
11 | 2 | Allen | Purchase reversal | The purchase weight applies at order creation. A subsequent Cancelled or Rejected applies the same weight negatively, aged from the creation timestamp of the order being reversed rather than from the cancellation. The two terms then cancel exactly under both methods. Verifiable on U16 against U17, which must differ by exactly the purchase contribution with neither carrying a negative raw. DS-008 v3.1 section 3.3 and DS-012 v2 section 5. | Actual build | RE-03 | Not started
12 | 2 | Allen | Sanity check the decay output | Query U04's scores sorted by raw. Home & Living must rank above Electronics with decay on, and Electronics must rank above it with decay off, which is what step 4 shows. If three month old Electronics still ranks top with decay on, either the half life is wrong in configuration or decay is not being applied. If Electronics does not lead with decay off, the generator has not given it the 1.2 times weight from task 8. | Build, exercised by the demo | RE-03 | Not started
13 | 2 | Kala and Allen | Agree the score row field names | raw, share, event_count, method, version, window, computed_at. Fixed on day 2 so the display script can be written against them on day 3 without guessing. Ten minutes. | Actual build | RE-02 | Not started
14 | 2 | Kala | Draft the narration for the ten demonstration steps | One or two sentences per step, written down rather than improvised. Includes the opening statement on constructed data. | For demo only |  | Not started
Day 3
15 | 3 | Allen | Method two, time windows | Three disjoint windows at 0 to 7, 8 to 30 and 31 to 90 days, weighted 0.5, 0.3 and 0.2. Disjoint, not nested: an event falls into exactly one window. A reversal falls into the window of the order it reverses. Writes under its own method value so both methods coexist in one store. | Actual build | RE-04 | Not started
16 | 3 | Kala | Display script | Reads the score store and prints a table: category, raw, share, event_count, with method, version and computed_at in the header. Three modes: one user, two users, one user under both methods side by side. Comparisons keep the same category ordering in both tables. Computes nothing itself. | For demo only |  | Not started
17 | 3 | Allen | Cold start handling in the read path | A user with no computed score returns which rung is serving them rather than an empty result. U07 is rung 2, the declared floor alone. U11 is rung 3, platform wide popularity computed over the window in P-27 across the demonstration collection. Rungs 4 and 5 fall through to rung 3 rather than returning empty, because the delivered score they point at exists for two of twelve users, and the fall-through is logged. | Actual build | RE-05 | Not started
18 | 3 | Kala and Allen | First dry run | All ten steps end to end. Anything that does not prove something is cut. Expect this one to be rough. | For demo only |  | Not started
Day 4
19 | 4 | Allen | Conformance check against the delivered score | With decay disabled, method one reproduces the delivered fixed weight score exactly on the restricted replay set in DS-008 v3.1 section 6.1. Equal, not close. The replay set excludes sub-threshold views, multi-category posts, non-canonical categories and reversed purchases, so U02, U03, U06, U08, U10, U11, U15 and U17 stay out of it. Blocked on D-01: if the delivered function cannot be invoked on a constructed event set, this compares against a reimplementation of its formula and asserts nothing. | Actual build | RE-08 | Not started
20 | 4 | Allen | Method and version stamped on every response | The read path returns the method and version alongside the score. Same stamp goes onto the impression event when that exists. | Actual build | RE-07 | Not started
21 | 4 | Kala and Allen | Second dry run, timed | Seventeen minutes against a fifteen minute slot, in order, with the narration. If it runs long, drop step 9, then step 8, then step 3. Protect step 10. | For demo only |  | Not started
22 | 4 | Kala | Prepare the four anticipated questions | Why the dataset is only twenty users, which method is better, why thirty days, and when this runs on real data. Answers ready rather than composed in the room. | For demo only |  | Not started
Fourteen of the twenty two tasks are engine code that ships. Ten of those are Allen's alone, two are the short joint schema agreements and two are Kala's parameter and dependency work. Twelve of the fourteen are Sprint 2 work brought forward by four days rather than extra effort spent on a demonstration. The eight demonstration items are Kala's, and the generator and display script both stay useful afterwards for regression checks.

## Not in these four days
Deliberately excluded ¦ so nobody builds it and nobody expects it
Each of these is Sprint 2 work. None is needed for the demonstration, and building any of them in this window takes time from the conformance check, which is the item that actually earns trust.
Excluded | Why it is not needed | When it lands
The variant layer and traffic split, PT-10 | Both methods compute and both are stored, but nothing routes live traffic between them. On the day you point the display script at one method or the other by hand. Say this in the room so nobody thinks a live A/B is running. The M1 comparison does not depend on the split in any case: both methods are computed for every user from stored data, and P-22 exists so a method can be switched rather than so it can be measured. | Sprint 2. Specification pending, see the open item below.
The scheduled refresh job, RE-06 | Run the computation by hand. A scheduler proves nothing on constructed data. | Sprint 2
The API contract and ingest endpoint, RE-00d | The display script reads the score store directly. The contract still needs agreeing with Aravinth, but it is not on the demonstration path. | Outstanding from Sprint 1
Rungs 4 and 5 of the fallback ladder, RE-05 | Rungs 2 and 3 are in scope and are demonstrated, by U07 and U11. Rungs 4 and 5 fall back to the delivered fixed weight score, which exists for two of twelve users, so there is nothing to demonstrate there yet. The fall-through from 4 and 5 to 3 is still built, under task 17. | Sprint 2
Any web page, chart or styling | A terminal table is enough. Half a day spent on a front end comes out of the conformance check. | Not planned
Anything about model quality | Constructed data can show the mechanism works as specified. It cannot show the specification is right. No numeric finding may be reported from test data. | Once the app carries users
One open item
PT-10 needs a written specification before Allen builds it. The position is that method selection sits entirely in the engine and the app is never involved: both methods compute offline, one is marked active in configuration, and a hashed user override sends a share of users to the challenger. What is not built is a per request comparator choosing the better output on the fly, because at serve time there is nothing to compare against and switching a user between methods makes the comparison permanently unanswerable.